## Cancelled permits
Cancellations/Emergency permits reported in January 2022
(information reported via email to Permit Cancellations inbox)
date/time of email notification | email received from | subject line - permit# | type of notification | details provided |  |  |  | cancelled by contractor or KCM
2021-12-01T14:42:47+00:00 | Mark.Swint@formacc.com | P21-11-543 | Cancellation | work completed, no further support is needed |  |  | 2021-12-01 | Contractor - Cancelled
2021-12-01T18:08:34+00:00 | Samuel.Bolt@masselec.com | P21-11-547 rev-1 SIT Dead Car Tow - Week of 11/29/2021 | Cancellation | cancelled due to the safety standdown that does not allow towing of LRVs at this time |  |  | 2021-12-01 | Contractor - Cancelled
2021-12-02T17:29:13+00:00 | Akshay.Thapar@kiewit.com | P21-11-537 | Cancellation | work completed faster than expected |  |  | 2021-12-02 | Contractor - Cancelled
2021-12-02T20:45:21+00:00 | linden.fisher@convergint.com | P21-11-548 Emergency Permit N11 Groundfault Trouble | Cancellation | troubleshoot N11 Groundfault , cancelled 1 day of emergency permit |  |  | 2021-12-02 | Contractor - Cancelled
2021-12-03T00:22:15+00:00 | david.shupe@soundtransit.org | P21-11-512 E2 Radio Outage | Cancellation | Dec. 2 cancellation -- poor coordination by contractor w/EIC |  |  | 2021-12-03 | Contractor - Cancelled
2021-12-06T15:16:18+00:00 | Alfred.Azen-KCRail@soundtransit.org | P21-11-524 Siemens Testing | Cancellation | 12/04/2021 cancelled due to multiple incidents (accident @ S. Webster St., radio outage, fire @ Sea Tac parking garage) leaving no available supervision for testing |  |  | 2021-12-06 | KCM - Cancelled
2021-12-06T15:41:51+00:00 | Jeff.Wachtel-KCRail@soundtransit.org | Siemens Testing | Cancellation | DUPLICATE for P21-11-524 |  |  | 2021-12-06 | duplicate report
2021-12-06T19:21:54+00:00 | Samuel.Bolt@masselec.com | P21-12-107 Live Wire Testing - Eastlink - Week of 12/06/2021 | Cancellation | cancelled due to the delay in the delivery of the final LRV for the four-car consist. |  |  | 2021-12-06 | Contractor - Cancelled
2021-12-06T19:21:45+00:00 | Samuel.Bolt@masselec.com | P21-12-106 OMF-E Camera Operation - Week of 12/06/2021 | Cancellation | cancelled due to the delay in the delivery of the final LRV for the four-car consist. |  |  | 2021-12-06 | Contractor - Cancelled
2021-12-07T00:41:10+00:00 | Todd.Eckhardt-KCRail@soundtransit.org | Siemens Testing | Cancellation | DUPLICATE for P21-11-524 |  |  | 2021-12-07 | duplicate report
2021-12-08T04:12:30+00:00 | Kavin.James-KCRail@soundtransit.org | P21-12-107 & P21-12-126 | Cancellation | 107 (live wire) cancelled by contractor for 12/12. 126 (vibration testing) cancelled per contractor for 12/9. | P21-12-126 |  | 2021-12-08 | Contractor - Cancelled
2021-12-09T07:29:18+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P21-12-121, Siemens dynamic cancelled | Cancellation | cancelled per contractor for 12/09/21 |  |  | 2021-12-09 | Contractor - Cancelled
2021-12-10T11:42:33+00:00 | carl.wheatley@collins.com | P21-12-231, Cancelled, (PIMS SCU Install & Interface Test - Group 7) | Cancellation | We (contractor) cancel permit (scheduled for 12/16 and 12/17 from 0001 to 0430), due to logistics and resource constraints |  |  | 2021-12-10 | Contractor - Cancelled
2021-12-10T15:16:12+00:00 | linktrackaccess@soundtransit.org | Cancellation of Permit P21-12-231 (PIMS SCU Install & Interface Test - Group 7) | Cancellation | DUPLICATE for P21-12-231 |  |  | 2021-12-10 | duplicate report
2021-12-10T21:51:22+00:00 | Paul.Dutton@mottmac.com | P21-12-214, Cancellation, Beacon Hill Tunnels C710 | Cancellation | Cancelled (by contractor) due to travel due to health concerns |  |  | 2021-12-10 | Contractor - Cancelled
2021-12-10T21:46:50+00:00 | Kathy.Morgan-KCRail@soundtransit.org | RE: P21-12-214 Track Access Request - Beacon Hill Tunnels C710 - Cancellation Request | Cancellation | DUPLICATE for P21-12-214 |  |  | 2021-12-10 | duplicate report
2021-12-14T21:08:04+00:00 | linktrackaccess@soundtransit.org | P21-12-240 EMERGENCY PERMIT- OCS power down 12/19 | Emergency | Nelson Trucking to move equipment in DSTT for TFD, requires power down |  |  | 2021-12-14 | Contractor - Emergency
2021-12-14T21:38:08+00:00 | Kathy.Morgan-KCRail@soundtransit.org | P21-12-241 EMERGENCY PERMIT | Emergency | Mass Elec Network Separation |  |  | 2021-12-14 | Contractor - Emergency
2021-12-14T22:59:42+00:00 | Samuel.Bolt@masselec.com | P21-12-210 RE: Live Wire Testing - Eastlink - Week of 12/13/2021 | Cancellation | Contractor not be ready for the evening |  |  | 2021-12-14 | Contractor - Cancelled
2021-12-14T22:59:50+00:00 | Samuel.Bolt@masselec.com | P21-12-237 LATE ACCEPTED OMF-E Camera Operation - Week of 12/13/2021 | Cancellation | Contractor unable to support the operation this week due to the delay in the fourth LRV |  |  | 2021-12-14 | Contractor - Cancelled
2021-12-15T07:37:54+00:00 | Robert.Garraway-KCRail@soundtransit.org | P21-12-213 | Cancellation | Cancelled due to no operators available to operate the work train which doubled as an active ice train |  |  | 2021-12-15 | KCM - Cancelled
2021-12-15T20:28:28+00:00 | Johnothon.Humphrey@masselec.com | P21-12-322 LATE ACCEPTED Live Wire Testing - Eastlink - Week of 12/20/2021 - Cancellation Request | Cancellation | Contractor not be ready for 12/20/21-12/23/21 |  |  | 2021-12-15 | Contractor - Cancelled
2021-12-16T23:45:21+00:00 | Johnothon.Humphrey@masselec.com | P21-12-210, Live Wire Testing | Cancellation | Live wire testing not ready |  |  | 2021-12-16 | Contractor - Cancelled
2021-12-17T02:09:37+00:00 | Kavin.James-KCRail@soundtransit.org | P21-12-219 (routine dynamic) & P21-12-220 Siemens (burn in) | Cancellation | cancelled per the contractor for this evening, Thursday, December 16th and Siemens Burn-in train has been cancelled for the rest of 2021 | P21-12-220 |  | 2021-12-17 | Contractor - Cancelled
2021-12-17T21:33:16+00:00 | DRobayo@henselphelps.com | P21-12-320 RE: M200 - Track Access request - Metal Panel Overlay 12.20.21 | Cancellation | cancelled by contractor, able to complete all the work this week |  |  | 2021-12-17 | Contractor - Cancelled
2021-12-21T07:21:16+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P21-01-313 and P21-01-314 | Cancellation | (Siemens) called LCC at approximately 1400 on 12/20/21 to cancel Permit 313 for all week and P 314 for tonight (12/21/21) |  |  | 2021-12-21 | Contractor - Cancelled
2021-12-21T22:45:34+00:00 | Mark.Swint@formacc.com | P21-12-310 | Cancellation | cancelled by contractor for the remainder of this permit. We are completed with the project and will not require any more support. |  |  | 2021-12-21 | Contractor - Cancelled
2021-12-22T06:56:16+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P21-12-314 | Cancellation | Cancelled 12/22/21 per LCC. Reason for cancellation is no test supervisor support is available |  |  | 2021-12-22 | KCM - Cancelled
2021-12-23T06:31:41+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P21-12-314 | Cancellation | no operator is scheduled for Siemens dynamic and permit 314 is cancelled for tonight (12/23/21). |  |  | 2021-12-23 | KCM - Cancelled
2021-12-23T15:52:43+00:00 | Perry.Knodle@kiewit.com | P21-12-418 KH/Shinn Fire StandPipe at Seattle Blvd for East Link Allocation Request for WK 12/27/2021 | Cancellation | Request cancelled after Wednesday planning meetings but before weekly plan finalized; support had been planned | P21-12-122 | P21-12-021 | 2021-12-23 | Contractor - Cancelled
2021-12-23T17:42:16+00:00 | Jason.Hawthorne-KCRail@soundtransit.org | P21-12-418 KH/Shinn Fire StandPipe at Seattle Blvd for East Link Allocation Request for WK 12/27/2021 | Cancellation | Cancelled by the contractor for all three days |  |  | 2021-12-23 | Contractor - Cancelled
2021-12-28T20:41:44+00:00 | Jeff.Wachtel-KCRail@soundtransit.org | Siemens testing, P21-12-419 and P21-12-420 | Cancellation | Siemens permits cannot be supported tonight (no support available), cancelled |  |  | 2021-12-28 | KCM - Cancelled
2021-12-29T17:39:00+00:00 | Jeff.Wachtel-KCRail@soundtransit.org | Siemens Testing, , P21-12-419 and P21-12-420 | Cancellation | Due to the snow event over the next 24 hrs and staffing issues Operations cancelled all Siemens testing over the next 2 days |  |  | 2021-12-29 | KCM - Cancelled
2021-12-30T16:31:24+00:00 | jcreager@kingcounty.gov | P22-01-112 OMF Tunnel DAS integration 1/3/2022 | Cancellation | PSERN cancelled, Moto has not confirmed personnel resources for the this installation |  |  | 2021-12-30 | Contractor - Cancelled
2022-01-03T16:30:54+00:00 | linktrackaccess@soundtransit.org | P22-01-105 updated Luminal Lighting_ Permit Request for week 01/03/22 (Revised) | Cancellation | Upgrading the LED fixtures at TIBS Station - request submitted late and accepted, then cancelled |  |  | 2022-01-03 | Contractor - Cancelled
2022-01-03T16:37:33+00:00 | alotfi@lumenal.com | P22-01-105 updated Luminal Lighting_ Permit Request for week 01/03/22 (Revised) | Cancellation | Upgrading the LED fixtures at TIBS Station - request submitted late and accepted, then cancelled |  |  | 2022-01-03 | Contractor - Cancelled
2022-01-03T16:46:02+00:00 | Arshia Lotfi <alotfi@lumenal.com> | P22-01-105, LED work at TIBS | Cancellation | Upgrading LED fixtures at TIBS - request submitted late/accepted, however cancelled until personnel COVID test results rec'd |  |  | 2022-01-03 | Contractor - Cancelled
2022-01-03T18:10:52+00:00 | linktrackaccess@soundtransit.org | P22-01-116, Break Bypass Testing | Cancellation | Cancelling the permit for 1/4/22 and 1/5/22, Break Bypass Mainline Testing (probably due to weather although reason not given) |  |  | 2022-01-03 | ST (Victor Sanchez) - Cancelled
2022-01-03T19:30:10+00:00 | alotfi@lumenal.com | P22-01-105, LED work at TIBS | Cancelled for 2 days, then work resumed | LED work to resume on 1/4 and 1/5 |  |  | 2022-01-03 | Reported to permit cancellations, included for info that Luminal work did resume
2022-01-04T18:08:48+00:00 | sglen@masselec.com | P22-01-102 - NOR-4S Signal Base Replacement 1/5/2022 | Cancellation | reported by contractor, KCM cancelled due to running ice trains |  |  | 2022-01-04 | KCM - Cancelled
2022-01-05T00:06:50+00:00 | Samuel.Bolt@masselec.com | P22-01-109 Camera Installation Permit-East Link- Week of 01/03/2022 | Cancellation | Canceled since Live Wire Testing will not begin this weekend |  |  | 2022-01-05 | Contractor - Cancelled
2022-01-05T14:52:15+00:00 | michael.erickson-kcrail@soundtransit.org | P22-01-110 E2 Optics DAS equipment work | Cancellation | P22-01-110 cancelled by contractor, no reason reported |  |  | 2022-01-05 | Contractor - Cancelled
2022-01-05T17:36:27+00:00 | victor.sanchez@soundtransit.org | P22-01-116, Break Bypass Testing | Cancellation | Due to LRV availability I’m cancelling this permit for 1/6 and 1/7 |  |  | 2022-01-05 | ST (Victor Sanchez) - Cancelled
2022-01-05T23:20:41+00:00 | CDiCristina@MassElec.com | P22-01-103 Mass Electric - Northgate Track Access Request | Cancellation | P22-01-103 cancelled by contractor, no reason reported |  |  | 2022-01-05 | Contractor - Cancelled
2022-01-07T10:51:03+00:00 | Laurie.Jacobs-KCRail@soundtransit.org | P22-01-125, Siemens vibration testing, Cancelled Due to No Staffing | Cancellation | Siemens vibration testing permit P22-01-125 canceled tonight due to lack of supervisor coverage |  |  | 2022-01-07 | KCM - Cancelled
2022-01-07T20:05:52+00:00 | Samuel.Bolt@masselec.com | P22-01-233 LATE ACCEPTED Camera Installation Permit-East Link- | Cancellation | Submitted late/accepted, then cancelled |  |  | 2022-01-07 | Contractor - Cancelled
2022-01-09T04:35:20+00:00 | Garrett.Berkey@masselec.com | P22-01-115 Cancellation, DCAM to the TIE in the MV Switchgear | Cancellation | Work completed and support for tonight or any other days for this permit specifically not needed |  |  | 2022-01-09 | Contractor - Cancelled
2022-01-10T15:20:15+00:00 | michael.erickson-kcrail@soundtransit.org | P22-01-218, DAS equipment work | Cancellation | Staffing issues on the ET Optic side |  |  | 2022-01-10 | Contractor - Cancelled
2022-01-10T17:31:10+00:00 | linktrackaccess@soundtransit.org | P22-01-223, camera install | Cancellation | Live Wire Testing being further pushed back, cancel the permit submitted for camera installation |  |  | 2022-01-10 | Contractor - Cancelled
2022-01-10T18:07:10+00:00 | michael.erickson-kcrail@soundtransit.org | P22-01-231, KCM filming Signals crew for recruitment video | Cancellation | KCM film crew member tested positive for COVID |  |  | 2022-01-10 | KCM - Cancelled
2022-01-11T18:17:08+00:00 | Kavin.James-KCRail@soundtransit.org | P22-01-226, Siemens Burn-in train | Cancellation | Per the contractor, Groundborne vibration testing has to be completed before we can continue with the burn-in train, cancelled per contractor for the remainder of the week, Jan 11th thru Jan 15th |  |  | 2022-01-11 | Contractor - Cancelled
2022-01-12T19:46:02+00:00 | Kavin.James-KCRail@soundtransit.org | P22-01-225, Siemens Routine Dynamic | Cancellation | Routine Dynamic testing has been cancelled due to lack of support |  |  | 2022-01-12 | KCM - Cancelled
2022-01-13T15:31:08+00:00 | GPotter@henselphelps.com | P22-01-232, Raising the OCS wire in the OMFE | Cancellation | Raising the OCS wire in the OMFE shop track M5 and M6, work completed day 1 of 4 |  |  | 2022-01-13 | Contractor - Cancelled
2022-01-14T17:31:41+00:00 | linktrackaccess@soundtransit.org | P22-01-234, emergency permit Corrpro Track Allocation Request for 1/15-16/22, IDS and Pioneer Sq. | Emergency | Setting data loggers and stray current testing | P22-01-123 | P22-01-622 | 2022-01-14 | KCM/ST - emergency
2022-01-19T04:38:12+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P22-01-321, Groundborne Vibration Testing cancelled for 01/18/22-01/19/22 | Cancellation | Cancelled by LCC for 01/18/22-01/19/22 due to no supervisor support available |  |  | 2022-01-19 | KCM - Cancelled
2022-01-21T21:35:43+00:00 | Kathy.Morgan-KCRail@soundtransit.org | P22-01-426, Siemens ATP testing -- Week of 1/24 | Cancellation | Cancelled after support discussions/planning for the week complete, so included in cancellation report |  |  | 2022-01-21 | Contractor - Cancelled
2022-01-24T15:21:58+00:00 | Mark.Gedosch@kpff.com | P22-01-435, DSTT GEC TO29 Fire Alarm Systems Assessment | Cancellation | It was determined that work can be done remotely through a teams meeting rather than meet onsite at OMF - member of the team tested COVID positive virtual backup plan was already in place |  |  | 2022-01-24 | Contractor - Cancelled
2022-01-24T20:51:01+00:00 | nharris@albireoenergy.com | P22-01-423, Albireo Energy Software and site condition audit | Cancellation | P22-01-423 due to a schedule change and are inability to support the staffing for the visit |  |  | 2022-01-24 | Contractor - Cancelled
2022-01-24T23:34:33+00:00 | Kavin.James-KCRail@soundtransit.org | P22-01-427, Siemens Burn-In & P22-01-442, Telvic Ride Along | Cancellation | Permit 427, Siemens Burn-In Train cancelled per contractor Jan 24th thru Jan 26th evenings. Permit 442, Telvic Ride Along, has been cancelled for the remainder of the week. | P22-01-442 |  | 2022-01-24 | Contractor - Cancelled
2022-01-27T07:48:13+00:00 | Nitten.Sanger-KCRail@soundtransit.org | P22-01-431 cancelled for 01/27/22, MEC Pole signs and anchor nuts to be installed in the Maple Leaf-Northgate Station Area, cancelled for 01/27/22 | Cancellation | Cancelled due to ice trains in the area of NGS and RVS - work requires power down which cannot be accommodated with ice trains running |  |  | 2022-01-27 | KCM - Cancelled
2022-01-28T14:35:55+00:00 | linktrackaccess@soundtransit.org | P22-01-508, ARINC PIMS SCU Install & Test | Cancellation | Cancelled after support discussions/planning for the week complete, so included in cancellation report | P22-01-150 | P22-01-020 | 2022-01-28 | soundtransit.org
END OF REPORT
Cancellations/Emergency permits reported in February 2022
(information reported via email to Permit Cancellations inbox)
172 permits processed for the month of February*
*(includes all permits processed and reviewed during the month, some cancelled during the review process due to lack of support or conflicting and/or higher priority work)
date/time of email notification | email received from | subject line - permit# | type of notification | details provided |  |  |  | cancelled by contractor or KCM | Contractor Name
2022-02-02T17:00:58+00:00 | Kavin.James-KCRail@soundtransit.org | P22-02-125 Siemens, Burn-In | Cancellation | Siemens Burn-in train has been cancelled per contractor for this evening, Wednesday, February 2nd thru Friday, February 4th. |  |  |  | Contractor - Cancelled | Siemens
2022-02-03T00:53:51+00:00 | Kathy.Morgan-KCRail@soundtransit.org | P22-01-509 Sound Transit/Lead Pencil Studio, UDS artwork video signal work | Cancellation | No details provided. |  |  |  | Contractor - Cancelled | Lead Pencil Studio
2022-02-04T22:46:49+00:00 | Vidal.Aguilar@formacc.com | P22-01-531 Forma, OMF-C Truck Shop Crane project | Cancellation | No details provided. |  |  |  | Contractor - Cancelled | Forma
2022-02-05T00:49:34+00:00 | kevin@nwsignal.org | P22-02-122, Photos of Cellular Antennas – UWS to NG Tunnels | Cancellation | Cancel P22-02-122 permit - work complete |  |  |  | Contractor - Cancelled | NW Signals
2022-02-07T22:27:11+00:00 | Nicholas.Routh-KCRail@soundtransit.org | P22-02-105 Mass Elec, Live Wire Testing, Eastlink | Cancellation | Permit 105 MEC East Link live wire testing has been cancelled per contractor for 2/7 & 2/8. |  |  |  | Contractor - Cancelled | Mass Electric
2022-02-10T18:51:04+00:00 | Samuel.Bolt@masselec.com | P22-02-105 Mass Elec, Live Wire Testing, Eastlink | Cancellation | There will be no live wire testing tonight, 2/10 |  |  |  | Contractor - Cancelled | Mass Electric
2022-02-10T23:13:04+00:00 | Kavin.James-KCRail@soundtransit.org | P22-02-115 Siemens, Burn-In | Cancellation | Permit 115, Siemens Burn-In train has been cancelled per contractor for the this evening, Thursday, Feb 10th thru Saturday, Feb 12th. |  |  |  | Contractor - Cancelled | Siemens
2022-02-14T02:25:24+00:00 | alotfi@lumenal.com | Permit P22-02-205 Lumenal, Upgrading LED fixtures at TIBS Station / No Work on Tuesday 02/15 | Cancellation | Permit P22-02-205 - Lumenal Light Replacement / No Work on Tuesday 02/15 |  |  |  | Contractor - Cancelled | Lumenal Lighting
2022-02-15T05:11:47+00:00 | Shannon.Shay-KCRail@soundtransit.org | P22-02-217 and 219 Siemens, testing permit(s) | Cancellation | Siemens testing on 02-09-2022 was canceled due to staffing. |  |  |  | KCM - Cancelled | Siemens
2022-02-15T23:09:12+00:00 | Kathy.Morgan-KCRail@soundtransit.org | P22-02-238 ST OET, Emergency Track Access Request, radio issues | Emergency | Troubleshoot radio issues between USS and PSS |  |  |  | ST OT - Emergency Request | Sound Transit Operations Technology
2022-02-15T23:58:54+00:00 | Samuel.Bolt@masselec.com | P22-02-231 Mass Elec, OMF-E Camera Operation | Cancellation | Completed today and support will not be needed tomorrow. |  |  |  | Contractor - Cancelled | Mass Electric
2022-02-16T02:24:49+00:00 | Kavin.James-KCRail@soundtransit.org | P22-02-217 and 219 Siemens, ATP & Burn-in | Cancellation | Permit 217, Siemens ATP & Permit 219, Burn-In train, has been cancelled due to lack of support. |  |  |  | KCM - Cancelled | Siemens
2022-02-17T01:07:11+00:00 | Paul.Dutton@mottmac.com | P22-02-201 Mott MacDonald, Structural inspection of back-of-house areas of BHS | Cancellation | Inspection was completed this morning February 16, 2022, any remaining time on the permit can be cancelled |  |  |  | Contractor - Cancelled | Mott MacDonald
2022-02-17T17:41:31+00:00 | linktrackaccess@soundtransit.org | P22-02-220 Sound Transit OT, Transfer Trip Restore Functionality ESR277 | Emergency update | Emergency Update to include one additional night of work. Traction Power agreed. |  |  |  | Contractor - Emergency Request | Sound Transit Operations Technology
2022-02-22T18:45:31+00:00 | david.shupe@soundtransit.org | P22-02-312 INIT/ST, TVM Replacement Prep - UDS | Cancellation | Work to be shifted to following week & included with track access request to be reviewed 2/23. Contractor will mobilize 2/28 rather than start actual work 2/28. |  |  |  | Contractor - Cancelled | INIT
2022-02-25T01:09:14+00:00 | Kavin.James-KCRail@soundtransit.org | P22-02-325 Siemens, Routine Dynamic & P22-02-326 Siemens Burn-In | Cancellation | Permit 325, Routine Dynamic has been cancelled this evening, Thursday, Feb 24th due to lack of support. Permit 326, Burn-In train has been cancelled this evening, Thursday, Feb 24th thru Saturday, Feb 26th per contractor. |  |  |  | KCM - Cancelled (325) Contractor - Cancelled (326) | Siemens
2022-02-25T14:33:37+00:00 | linktrackaccess@soundtransit.org | P22-02-339 ST IT, Emergency access to the Comm Room of University Street Station | Emergency | Network switch replacement at USS to correct network issues affecting station PLC’s, TVM’s, and other networked equipment. |  |  |  | ST IT- Emergency Request | Sound Transit Information Technology
2022-02-25T21:19:26+00:00 | alotfi@lumenal.com | P22-02-408 Lumenal, Upgrading the LED fixtures at Mt Baker Station | Cancellation | Due to material delay, cancel the scheduled work on Monday 02/28, start on Tuesday 03/01 instead |  |  |  | Contractor - Cancelled | Lumenal Lighting
2022-02-28T11:52:45+00:00 | Jeremy.Thomas-KCRail@soundtransit.org | P22-02-428 Wilson Ihrig, Rail/Rolling Noise Characterization Study | Cancellation | cancelled on this date per contractor due to extremely wet weather conditions that would interfere with equipment setup and data collection. |  |  |  | Contractor - Cancelled | Wilson Ihrig
END OF REPORT
Cancellations/Emergency permits reported in March 2022
(information reported via email to Permit Cancellations inbox)
162 permits processed for the month of March*
*(includes all permits processed and reviewed during the month, some cancelled during the review process due to lack of support or conflicting and/or higher priority work)
date/time of email notification | email received from | subject line - permit# | type of notification | details provided |  |  |  | cancelled by contractor or KCM | Contractor Name
2022-03-05T05:02:37+00:00 | Laurie.Jacobs-KCRail@soundtransit.org | P22-02-430 Siemens Routine Dynamic Cancelled Lack of Staffing for 03/05 | Cancellation | No supervisors. Link 5 pulled into LCC. Link 1 special assignment at TIBS. |  |  |  | KCM - Cancelled | Siemens
2022-03-08T21:12:37+00:00 | Kavin.James-KCRail@soundtransit.org | P22-03-125 Siemens Burn-In | Cancellation | cancelled per contractor for this evening, March 8th thru March 12th. |  |  |  | Contractor - Cancelled | Siemens
2022-03-09T08:20:27+00:00 | Robert.Garraway-KCRail@soundtransit.org | P22-03-124 Cancelled | Cancellation | Permit was canceled by the Track department due to higher priority permit (P22-03-120 ARM Track Inspection) needing to take place in the area (C755) |  |  |  | KCM - Cancelled | Siemens
2022-03-09T20:23:11+00:00 | linktrackaccess@soundtransit.org | P22-03-133 Emergency Permit Track Access request to troubleshoot IT connection to Pilot Next Gen TVMs | Emergency | Troubleshoot IT connection to Pilot Next Gen TVMs |  |  |  | ST KCM - Emergency Request | INIT/ST
2022-03-15T15:51:27+00:00 | Akshay.Thapar@kiewit.com | Permit # P22-03-224 | Cancellation | Permit canceled and not needed anymore for next week. Mass Electric Access to Kirkland East Signals House at OMFE. |  |  |  | Contractor - Cancelled | Mass Electric
2022-03-16T14:43:09+00:00 | Kavin.James-KCRail@soundtransit.org | P22-03-229 Siemens Burn-In | Cancellation | Permit 229, Siemens Burn-In train has been cancelled per contractor, for March 15th thru March 19th |  |  |  | Contractor - Cancelled | Siemens
2022-03-18T17:18:15+00:00 | Kathy.Morgan-KCRail@soundtransit.org | P22-03-242 KCM MEC Signals Emergency Track Access Request for EMI Hangers 03.18.2022 | Emergency | MEC will walk the Northgate Tunnel and grind down 19 EMI Hanger nuts and washers. |  |  |  | Contractor - Emergency Request | Mass Electric
2022-03-21T04:14:37+00:00 | Robert.Garraway-KCRail@soundtransit.org | P22-03-340 canceled tonight 03/20/22 by contractor. First date only. | Cancellation | Deangelo Contracting herbicide application of the ballasted trackway, Signal houses, TPSS grounds and OMF yard. Includes both daytime and non-revenue hours. |  |  |  | Contractor - Cancelled | Deangelo Contracting
2022-03-21T07:25:30+00:00 | Garrett.Berkey@masselec.com | Permit Cancellations 3/21 - Permits P22-03-331 and 338 - EPMS Server Installation and Functionality Testing and Terminal Strip Wiring Installation - UDS Transformer Cages | Cancellation | Permits P22-03-331 and 338 cancelled tonight - no personnel from the MEC/Siemens side available. |  |  |  | Contractor - Cancelled | Mass Electric and Siemens
2022-03-21T16:24:36+00:00 | michael.erickson-kcrail@soundtransit.org | Permit P22-03-341 | Cancellation | Re-pull Kirkland North switch heater cabinet feeder and terminate in Kirkland North Signal House - OMFE, Mass Electric cancelled for the week per Alex. |  |  |  | Contractor - Cancelled | Mass Electric
2022-03-22T17:28:24+00:00 | linktrackaccess@soundtransit.org | P22-03-345 emergency track access request | Emergency | Site inspection of LRV delivery slabs at OMF Central. Take measurements of the 2 slabs and check difference between the two levels. |  |  |  | ST/PM-BLID - Emergency Request | ST/PM-BLID
2022-03-23T18:45:31+00:00 | Nicholas.Routh-KCRail@soundtransit.org | P22-03-318 cancelled for 3/23/22 | Cancellation | SIT Live Wire with 4-Car KI consist- Construction Side, Leaving from OMFE |  |  |  | Contractor - Cancelled | Mass Electric
2022-03-24T15:43:30+00:00 | Samuel.Bolt@masselec.com | P22-03-318 OCS Live Wire Re-Test - cancelled for 3/25/22 | Cancellation | SIT Live Wire with 4-Car KI consist- Construction Side, Leaving from OMFE |  |  |  | Contractor - Cancelled | Mass Electric
2022-03-25T19:35:22+00:00 | Akshay.Thapar@kiewit.com | P22-03-419 Track Access Permit for N830 Completion Report | Cancellation | N830 Completion Report - site visit, taking photos with escort to Comm Rooms |  |  |  | Contractor - Cancelled | Mass Electric
2022-03-28T19:18:55+00:00 | Kavin.James-KCRail@soundtransit.org | P22-03-426 Siemens Burn-In | Cancellation | Cancelled March 28th thru April 2nd |  |  |  | Contractor - Cancelled | Siemens
2022-03-28T22:35:42+00:00 | bill.gardner@soundtransit.org | Track Allocation Permit P22-03-436 CANCELLED | Cancellation | Site visit and inspection only for prospective bidders for the upcoming DSTT State of Good Repair Track Bonds |  |  |  | ST - Cancelled | ST - DECM
2022-03-30T12:51:53+00:00 | Kavin.James-KCRail@soundtransit.org | P22-03-427 Siemens Routine Dynamic | Cancellation | Siemens Routine Dynamic was cancelled due to lack of support for Tuesday evening, March 29th |  |  |  | KCM - Cancelled | Siemens
2022-03-30T18:36:07+00:00 | linktrackaccess@soundtransit.org | P22-03-441 Emergency Permit Request UWS Map Faults | Emergency | Map Faults on UW Station Panel |  |  |  | Contractor - Emergency Request | Convirgent
2022-03-31T13:51:13+00:00 | linktrackaccess@soundtransit.org | P22-03-440 | Emergency | Herbicide application of the Signal houses, TPSS grounds and OMF yard. |  |  |  | Contractor - Emergency Request | Deangelo Contracting
2022-03-31T18:54:03+00:00 | linktrackaccess@soundtransit.org | P22-03-442 OMFE - Emergency Track Access Request - ETS Circuit Issue - 3.28.2022 | Emergency | Troubleshoot the Emergency Trip Circuitry – OMFE |  |  |  | Contractor - Emergency Request | C3M Power Systems/Valley Electric
2022-03-31T20:25:21+00:00 | linktrackaccess@soundtransit.org | RE: P22-03-442 OMFE - Emergency Track Access Request - ETS Circuit Issue - 3.28.2022 | Emergency | Troubleshoot the Emergency Trip Circuitry – OMFE |  |  |  | KCM - updated per Traction Power request to add dates | C3M Power Systems/Valley Electric
2022-03-31T20:25:21+00:00 | Laurie.Jacobs-KCRail@soundtransit.org | P22-03-427 Anthony from Siemens called at 2130 to cancel routine dynamic for tonight. | Cancellation | Siemens Routine Dynamic was cancelled for evening of March 31 |  |  |  | Contractor - Cancelled | Siemens
END OF REPORT
Cancellations/Emergency permits reported in DECEMBER 2022
(information reported via email to Permit Cancellations inbox)
137 in reporting period
*(permits processed to approval with support arrangements in place, then subsequently cancelled)
date/time of email notification | email received from | subject line - permit# | type of notification | details provided |  |  |  | cancelled by contractor or KCM | Contractor Name
Fri 7/1/2022 12:47 PM | Michael.Rafferty <Michael.Rafferty@masselec.com> | P22-07-121 cancellation | Cancellation | We must cancel permit P22-07-121 due to overlapping work @ IDS which takes precedent. |  |  |  | Contractor - Cancelled | MEC
Sun 7/3/2022 8:37 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P22-07-129 and 133 | Cancellation | Permit 129, Siemens Burn train & Permit 133, Siemens ATP testing has been cancelled per contractor for the evening, July 5th 2022. |  |  |  | Contractor - Cancelled | Siemens
Wed 7/6/2022 3:34 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-07- 129 Siemens burn in has been cancelled per contractor for 7/6 and 7/7 | Cancellation | Permit P22-07- 129 Siemens burn in has been cancelled per contractor for 7/6 and 7/7 |  |  |  | Contractor - Cancelled | Siemens
Thu 7/7/2022 9:47 AM | Cornell, Molly (KCRail) <molly.cornell-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-137 EMERGENCY WORK PERMIT | Emergency | DC Group - Emergency UPS Repair at SeaTac |  |  |  | KCM/Facililties & Contractor - Requested | DC Group
Fri 7/8/2022 11:38 AM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-07-129 is canceled per contractor for today and 7/9 | Cancellation | Permit P22-07-129 Siemens Burn In is canceled per contractor for today and 7/9 |  |  |  | Contractor - Cancelled | Siemens
Tue 7/12/2022 9:12 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-206 Southcenter OCS Wire Replacement 755-205 to 755-238 Track Access Request week of 7/12 | Cancellation | P22-07-206 Southcenter OCS Wire Replacement 755-205 to 755-238 Track Access Request week of 7/12 |  |  |  | ST - Cancelled | Sound Transit - Ringo Wong
Tue 7/12/2022 3:48 PM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | P22-07-203 Track Access Request for SIT Dead Car Clearance Equipment Installation Week of 7/11 | Cancellation | Please cancel permit P22-07-203 for the LRV car clearance equipment installation that was scheduled for Thursday July 14th. |  |  |  | Contractor - Cancelled | MEC
Tue 7/12/2022 3:50 PM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | P22-07-204 Track Access Request for SIT Car Mover Clearance Week of 7/11 | Cancellation | Please cancel permit P22-07-204 for LRV car mover and dead car tow clearance that was scheduled for Thursday July 14th and Friday July 15th. |  |  |  | Contractor - Cancelled | MEC
Fri 7/15/2022 8:40 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-239 - Emergency Permit - CORRPRO last minute track allocation request | Emergency | Late/emergency track allocation request. The work was coordinated in advance with Traction Power. |  |  |  | KCM/Facililties & Contractor - Requested | Corrpro
Fri 7/15/2022 8:44 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-238 Emergency Permit DC Group UPS Repair SeaTac - 7.15.22 | Emergency | DC Group - Emergency UPS Repair at SeaTac |  |  |  | KCM/Facililties & Contractor - Requested | DC Group
Fri 7/15/2022 3:24 PM | Mark Swint <Mark.Swint@formacc.com> | Permit P22-07-324 | Cancellation | Manpower, equipment, and access issues, Western Exterminators/Forma are not going to be able to meet The deadline of next week to lift the snorkels off the platform. cancel permit for the Barnhardt Crane pick. |  |  |  | Contractor - Cancelled | Forma
Sat 7/16/2022 1:12 AM | Jacobs, Laurie (KCRail) <Laurie.Jacobs-KCRail@soundtransit.org> | Siemens Routine Dynamic P22-07-232 XLD Due to Staffing: | Cancellation | Routine Dynamic canceled due to lack of field supervisors for the morning of 7/16 |  |  |  | KCM Cancelled | Siemens
Mon 7/18/2022 10:42 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | 022-07-14 Permit P22-07 232 | Cancellation (reported late to Track Access vs Permit Cancellations) | Testing was cancelled tonight (Thursday, July 14, 2022 3:30 AM). We were going to use LRV 251 again. Jack was changing out the speed sensor to try and fix the problem we had yesterday, however he did not have a new one. |  |  |  | KCM Cancelled | Siemens
Mon 7/18/2022 12:06 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-317 REV-1 - C11 Signal Fiber Testing - 7/22/2022 and 7/23/2022 | Emergency - permit was cancelled and then "revived" the following Monday, so reporting as an emergency permit | As discussed and agreed to by Traction Power & Signals Chiefs, previously cancelled permit has been revised as Rev-1. Will be reported as an emergency/late permit. |  |  |  | KCM/Traction Power & Signals & Contractor - Requested | MEC
Mon 7/18/2022 12:26 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-338 BHS Permit | Emergency | Johnson Controls standard maintenance - request was late, but processed as requested by KCM |  |  |  | KCM/SCADA & Contractor - Requested | Johnson Controls
Tue 7/19/2022 9:56 PM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | Permit P22-07-330 cancelled for night of 7/19-7/20 | Cancelled | Siemens Groundborne Vibration Testing Cancelled due to lack of field personnel |  |  |  | KCM Cancelled | Siemens
Wed 7/20/2022 11:21 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-339 - ADA Dome Tile Demobilization at Columbia City | Emergency | Work completed early - demob needed |  |  |  | KCM/ST & Contractor - Requested | Waters Construction
Wed 7/20/2022 5:31 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-07-333, Siemens Burn-In train has been cancelled per contractor for this evening, Wednesday, July 20th | Cancelled | Permit 333, Siemens Burn-In train has been cancelled per contractor for this evening, Wednesday, July 20th |  |  |  | Contractor - Cancelled | Siemens
Thu 7/21/2022 6:42 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-07-333, Siemens Burn-In train has been cancelled per contractor for this evening, Thursday, July 21st | Cancelled | Permit 333, Siemens Burn-In train has been cancelled per contractor for this evening, Thursday, July 21st |  |  |  | Contractor - Cancelled | Siemens
Thu 7/21/2022 11:15 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-07-331 Siemens ATP testing cancelled 7/22 | Cancelled | Siemens cancelled ATP testing under permit 331 for 7/22 0001 – 0430 this evening at 23:10 |  |  |  | Contractor - Cancelled | Siemens
Fri 7/22/2022 8:06 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permits P22-07-331, Siemens ATP testing & Permit P22-07-333, Siemens Burn-In train, cancelled | Cancelled | Permits 331, Siemens ATP testing & Permit 333, Siemens Burn-In train, has been cancelled per contractor for this evening, Friday, July 22nd |  |  |  | Contractor - Cancelled | Siemens
Sat 7/23/2022 3:34 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-07-333, Siemens Burn-In train, has been cancelled due to lack of support for today, Saturday, July 23rd | Cancelled | Permit 333, Siemens Burn-In train, has been cancelled due to lack of support for today, Saturday, July 23rd |  |  |  | KCM Cancelled | Siemens
Mon 7/25/2022 1:20 PM | Marguerite Clark <Marguerite.Clark@bnbuilders.com> | P22-07-436 CANCELLED 4536 Brooklyn - Tunnel Monitoring - Track Access Permit - 7/25 | Cancelled | Cancelled for entire week. We are currently trying to work out with Sound Transit Legal to execute the license agreement. We will be on the call this week for our additional permit for access requested 8/1. |  |  |  | Contractor - Cancelled | BNBuilders/Sixense
Mon 7/25/2022 2:17 PM | Akshay.Thapar <Akshay.Thapar@kiewit.com> | Permit Number P22-07-428 Cancellation | Cancelled | MEC will be canceling permit number P22-07-428. The permit is canceled for the whole week. |  |  |  | Contractor - Cancelled | MEC
Tue 7/26/2022 6:31 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-07-424, Siemens Routine Dynamic has been cancelled per contractor for this evening, Tuesday, July 26th | Cancelled | Permit P22-07-424, Siemens Routine Dynamic has been cancelled per contractor for this evening, Tuesday, July 26th |  |  |  | Contractor - Cancelled | Siemens
Tue 7/26/2022 11:14 PM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-07-403 MEC Pre-Commissionings Signals Testing, P22-07-420 ME/SECA Field Testing E750, and P22-07-434 SIEMENS LRV ROUTINE DYNAMIC - no-show and cancelled at the tie-in this evening. | Cancelled | P22-07-403, P22-07-420, P22-07-434, P22-07-436 (actually cancelled earlier in the week) were no-show and cancelled at the tie-in this evening. |  |  |  | Contractor - Cancelled by default (no show at tie in meeting) | MEC, SECA and Siemens
Wed 7/27/2022 4:44 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-415 Big Mountain Elec - Ballast Replacement, Cancelled | Cancelled | P22-07-415 Big Mountain Elec - Art lighting, Cancelled |  |  |  | Contractor - Cancelled | Big Mountain
Wed 7/27/2022 6:24 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P22-07-434 Siemens Routine Dynamic | Cancelled | P22-07-434 Siemens Routine Dynamic |  |  |  | Contractor - Cancelled | Siemens
Thu 7/28/2022 5:12 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-07-433, Siemens Burn-In & Permit P22-07-434, Siemens Routine Dynamic has been cancelled due to lack of support for this evening, Thursday, July 28th | Cancelled | Permit P22-07-433, Siemens Burn-In & Permit P22-07-434, Siemens Routine Dynamic has been cancelled due to lack of support for this evening, Thursday, July 28th |  |  |  | KCM Cancelled | Siemens
Fri 7/29/2022 7:14 AM | Cornell, Molly (KCRail) <molly.cornell-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-07-440 Emergency Permit- RE: Northgate Power Problem [#34] | Emergency | P22-07-440 Emergency Permit- RE: Northgate Power Problem [#34] |  |  |  | KCM/Signals & Contractor - Requested | Elcon
Fri 7/29/2022 6:39 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P-433 Siemens Burn-In & P-434 Siemens Routine Dynamic | Cancelled | Permit 433, Siemens Burn-In & Permit 434, Siemens Routine Dynamic has been cancelled due to lack of support for this evening, Friday, July 29th |  |  |  | KCM Cancelled | Siemens
Sat 7/30/2022 1:41 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit 433, Siemens Burn-In has been cancelled due to lack of support for today, Saturday, July 30th. | Cancelled | Permit 433, Siemens Burn-In has been cancelled due to lack of support for today, Saturday, July 30th. |  |  |  | KCM Cancelled | Siemens
Mon 8/1/2022 11:05 AM | Danelle Rempfer <DanelleR@groupmcs.com> | P22-08-120 Permit Request for the week of August 1st | Cancellation | Parts not received due to shipping delays |  |  |  | Contractor - Cancelled | Mechanical & Control Services
Mon 8/1/2022 12:17 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | Emergency Permit Request - ABB Power Module Install - UDS | Emergency | Emergency Fan Power Module installation at UDS - parts in |  |  |  | KCM/Facililties & Contractor - Requested | Facilities and ABB
Monday, August 1, 2022 4:40 PM | ahmed.idrees@soundtransit.org> | P22-08-101_ST_Rockwell SCADA Restore Test - Phase 3 - Cloud BMS Restore_OMF_3rd Floor | Cancellation | Team member working at the OMFC tested Covid positive today |  |  |  | ST - Cancelled | ST and Rockwell
Tue 8/2/2022 6:45 PM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | P22-08-104 for Dead Car Clearance device installation at OMF- | Cancellation | Please cancel permit P22-08-104 for Dead Car Clearance device installation at OMF-E that was scheduled for tomorrow Wednesday 8/2/22 |  |  |  | Contractor - Cancelled | MEC
Tue 8/2/2022 6:49 PM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | P22-08-105 Track Access Request Car Mover Clearance 080422 | Cancellation | Please cancel permit P22-08-105 for car move clearance and LRV dead car tow that was scheduled for Thursday 8/4/22 and Friday 8/5/22. |  |  |  | Contractor - Cancelled | MEC
Wed 8/3/2022 5:31 PM | Fitzgerald, Preston (KCRail) <Preston.Fitzgerald-KCRail@soundtransit.org> | Permit P22-08-131 work complete | Cancellation | Work complete, permit not needed - P22-08-131 on 08/04/2022. Visual inspection of station elec equipment - WLS/Pine St. Vent Facility. |  |  |  | Contractor - Cancelled | WSP
Fri 8/5/2022 1:15 PM | Marguerite Clark <Marguerite.Clark@bnbuilders.com> | P22-08-226 CANCELLATION 4536 Brooklyn - Tunnel Monitoring | Cancellation | ST & Our Owner have not come to a license agreement |  |  |  | Contractor - Cancelled | BNBuilders
Sun 8/7/2022 8:32 PM | Nick.Conley@soundtransit.org> | P22-08-201 Rockwell SCADA Restore Test - Phase 2 , Cancellation Due to illness | Cancellation | P22-08-201 Rockwell SCADA Restore Test - Phase 2 - Local TCS Restore_OMF_3rd Floor - Cancellation Due to illness |  |  |  | Contractor - Cancelled | Rockwell
Mon 8/8/2022 4:17 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-202 Track Access Request 8.7.22-8.12.22_Site Walk | Cancellation | P22-08-202 Cancelled due to Stacy Whitbeck and Railworks not having current ROW training cards. |  |  |  | Contractor - Cancelled | Stacy Whitbeck and Railworks
Tue 8/9/2022 10:34 PM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-08-221 - Siemens ATP | Cancellation | Due to lack of support personnel, permit 221, Siemens ATP, was cancelled for this evening |  |  |  | KCM - Cancelled | KCM Ops
Wed 8/10/2022 6:17 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-230 OMF Antenna install - one of scheduled days cancelled | Cancellation | P22-08-230 OMF Antenna install - one of scheduled days cancelled due to unavailable equipment |  |  |  | Contractor - Cancelled | CTS
Thu 8/11/2022 3:27 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-220, Siemens Burn-In train has been cancelled | Cancellation | Permit 220, Siemens Burn-In train has been cancelled per contractor for this evening, Thursday, August 11th |  |  |  | Contractor - Cancelled | Siemens
Fri 8/12/2022 6:07 AM | Larson, Mike (KCRail) <Mike.Larson-KCRail@soundtransit.org> | P22-08-333 Track Access Request- ARM Sperry UT Testing - Cancelled | Cancellation | P22-08-333 Track Access Request- ARM Sperry UT Testing - Contingenct permit, Cancelled |  |  |  | Contractor - Cancelled | ARM
Fri 8/12/2022 11:48 AM | Wheatley, Carl IMS <carl.wheatley@collins.com> | Permit P22-08-320 Cancellation | Cancellation | Permit P22-08-320 for the week beginning 8/15 (PIMS SIT 08-15-2022) can be cancelled |  |  |  | Contractor - Cancelled | Wabtec
Fri 8/12/2022 3:01 PM | Conley, Nick <Nick.Conley@soundtransit.org> | P22-08-304 - Rockwell SCADA Restore Test - Phase 2 - Local TCS Restore_OMF_3rd Floor - Cancellation due to ongoing staff shortage | Cancellation | The ST Operations Technology team is unable to staff for this event. The Phase 2 work scheduled for 8/22 – 8/23 has been cancelled. |  |  |  | ST - Cancelled | Rockwell
Tue 8/16/2022 9:34 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-332, Siemens Burn-In train was cancelled | Cancellation | Permit P22-08-332, Siemens Burn-In train was cancelled per contractor for yesterday evening, Monday August 15th. |  |  |  | Contractor - Cancelled | Siemens
Tue 8/16/2022 2:34 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-332, Siemens Burn-In train was cancelled | Cancellation | Permit 332, Siemens Burn-In train has been cancelled per contractor for this evening, Tuesday August 16th. |  |  |  | Contractor - Cancelled | Siemens
Tue 8/16/2022 3:05 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-334 Task Order 42.00 - Sprague Pest Work in Pigeon Alley | Cancellation | P22-08-334 Task Order 42.00 - Sprague Pest Work in Pigeon Alley - Work Complete - Day 2 cancelled |  |  |  | Contractor - Cancelled | Sprague Pest
Wed 8/17/2022 2:52 PM | Wheatley, Carl IMS <carl.wheatley@collins.com> | Permit P22-08-418 Cancellation | Cancellation | Permit P22-08-418 for the week beginning 8/22 (PIMS SIT 08-22-2022) can be cancelled |  |  |  | Contractor - Cancelled | Wabtec
Wed 8/17/2022 6:54 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-332, Siemens Burn-In train has been cancelled | Cancellation | Permit P22-08-332, Siemens Burn-In train has been cancelled per contractor for this evening, Wednesday, August17th. |  |  |  | Contractor - Cancelled | Siemens
Thu 8/18/2022 2:20 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-339 Emergency Permit application For UW FLS Restoration (FACP updates) | Emergency | P22-08-339 Emergency Permit application For UW FLS Restoration (FACP updates) |  |  |  | KCM & Contractor - Requested | Convergint
Thu 8/18/2022 4:55 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-332, Siemens Burn-In train has been cancelled per contractor for this evening, Thursday, August 18th. | Cancellation | Permit P22-08-332, Siemens Burn-In train has been cancelled per contractor for this evening, Thursday, August 18th. |  |  |  | Contractor - Cancelled | Siemens
Fri 8/19/2022 7:48 AM | Andrew.Facemyer <AFacemyer@masselec.com> | P22-08-427 Permit Request (PIMS work) - Week of 8/22 | Cancellation | due to the circumstances around permit #410 being shortened, cancel this permit for next week |  |  |  | Contractor - Cancelled | MEC
Fri 8/19/2022 11:59 AM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-420 CANCELLED Phase 4 Rockwell SCADA Restore Tests | Cancellation | Due to cancellation impacting Phase 2 (TCS Local Restore Validation) move this work to the week of 8/29/2022. |  |  |  | Contractor - Cancelled | Rockwell
Tue 8/23/2022 6:54 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-422 – cancelled the rest of the week, reported by contractor | Cancellation | IWS (pressure washing) will need to cancel the rest of this weeks permitted time as planned due to vehicle theft. |  |  |  | Contractor - Cancelled | IWS
Wed 8/24/2022 5:48 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-429, Siemens Routine Dynamic testing was cancelled per contractor | Cancellation | Permit P22-08-429, Siemens Routine Dynamic testing was cancelled per contractor for Tuesday evening, August, 23rd. |  |  |  | Contractor - Cancelled | Siemens
Wed 8/24/2022 6:23 AM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P08-29-2022 can be cancelled | Cancellation | PIMS SIT 08-29-2022 can be cancelled. We are initiating other work, PIMS SCU testing for the 09-05-2022 week, covered under a separate permit request. |  |  |  | Contractor - Cancelled | Wabtec
Wed 8/24/2022 7:14 AM | Rich Lehl <rich@richlehl.com> | Cancellation of Permit # P22-08-414 (art work cleaning) | Cancellation | employee called in sick this morning and won’t be able to work |  |  |  | Contractor - Cancelled | Rich Lehl Studio
Thu 8/25/2022 9:30 PM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-08-429 Siemens Route Dynamic Testing | Cancellation | Due to lack of on duty supervisors, permit 429 was cancelled for this evening |  |  |  | KCM - Cancelled | KCM Ops
Fri 8/26/2022 1:52 PM | Gon, Awa Collins <awa.gon@collins.com> | Please cancel reminder permit P22-08-402 SCADA TCS Maintenance Release - Delivery PIMS Interface Over Existing Lines | Cancellation | Please cancel reminder permit P22-08-402 - unable to complete enough work night 1 to continue the rest of the week |  |  |  | Contractor - Cancelled | Rockwell Collins
Fri 8/26/2022 9:25 PM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-08-429 Siemens Route Dynamic Testing | Cancellation | Permit 429 for this evening was cancelled by me due to lack of supervisor support at 2120 |  |  |  | KCM - Cancelled | KCM Ops
Sun 8/28/2022 12:51 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-08-507 LINK TRACK ALLOCATION REQUEST - EMI Hanger Mitigation | Cancellation | This permit can be cancelled as the work has been completed this week |  |  |  | Contractor - Cancelled | MEC
Wed 8/31/2022 8:02 PM | Fitzgerald, Preston (KCRail) <Preston.Fitzgerald-KCRail@soundtransit.org> | Siemens Burn In Permit P22-08-527 | Cancellation | Brian from Siemens called LCC 19:53 to Cancel the Burn in for tonight. This was due to Vehicle issues in the yard. |  |  |  | Contractor - Cancelled | Siemens
Fri 9/2/2022 1:46 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Siemens Burn In Permit P22-08-527 | Cancellation | Permit P22-08-527, Siemens Burn-In train has been cancelled per contractor for Sept 2 & 3 |  |  |  | Contractor - Cancelled | Siemens
Tue 9/6/2022 10:44 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Siemens Burn In Permit P22-09-127 | Cancellation | Permit P22-09-122, Siemens Burn-In train has been cancelled per contractor for Sept 6th and 7th |  |  |  | Contractor - Cancelled | Siemens
Thu 9/8/2022 7:06 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-08-122, Siemens Burn-In train has been cancelled per contractor for Sept 8th thru 10th | Cancellation | Permit P22-09-122, Siemens Burn-In train has been cancelled per contractor for Sept 8th thru 10th |  |  |  | Contractor - Cancelled | Siemens
Wed 9/7/2022 2:07 PM | Roberts, Maria (KCRail) <Maria.Roberts-KCRail@soundtransit.org> | Corrpro Rail to Earth Resistence testing and Data Loggers, P22-09-114 and P22-09-113 cancelled | Cancellation | Corrpro P22-09-114 with TP and P22-09-113 with Signals cancelled for the rest of the week. |  |  |  | Contractor - Cancelled | Corrpro
Mon 9/12/2022 7:06 AM | Dale Lindemuth <dlindemuth@aegion.com> | P22-09-219 Cancellation for 9/13/202 | Cancellation | P22-09-219 Corrpro Track Allocation Request - 9/13-9/16/2022 - Rail-to-Ground Resistance Testing, Angle Lake to Airport ***Cancellation for 9/13/202 |  |  |  | Contractor - Cancelled | Corrpro
Tue 9/13/2022 8:44 AM | Dale Lindemuth <dlindemuth@aegion.com> | P22-09-219 cancelled for 9/14 non-revenue | Cancellation | Cancel Permit P22-09-219 for tonight as well (9/14 non-revenue). We’ll advise tomorrow morning for the remainder of the week – 9/15 & 9/16. |  |  |  | Contractor - Cancelled | Corrpro
Tue 9/13/2022 10:05 AM | Salvador Benitez <salvador.benitezjr@c3mpowersystems.com> | P22-09-228 Cancellation - replace section insulators OMFE shop | Cancellation | Cancel this permit for today and the remainder of the week. Crew has outdated Right of Way Training Cards and therefore cannot be onsite. |  |  |  | Contractor - Cancelled | C3M Power
Tue 9/13/2022 4:26 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-09-223 Siemens burn in has been cancelled per contractor 9/12 through 9/17. | Cancellation | Permit P22-09-223 Siemens burn in has been cancelled per contractor 9/12 through 9/17. |  |  |  | Contractor - Cancelled | Siemens
Wed 9/14/2022 7:53 AM | Dale Lindemuth <dlindemuth@aegion.com> | P22-09-219 Corrpro Rail to Earth resistence testing cancel the remainder of this permit – for 9/15 & 9/16. | Cancellation | P22-09-219 Corrpro Rail to Earth resistence testing cancel the remainder of this permit – for 9/15 & 9/16. |  |  |  | Contractor - Cancelled | Corrpro
Wed 9/14/2022 5:41 PM | mylinda.sneed@soundtransit.org | P22-09-229 Cancelled, Artwork video signal testing and punchlist work at UDS. | Cancellation | P22-09-229 Cancelled, Artwork video signal testing and punchlist work at UDS. |  |  |  | ST - Cancelled | STArt/Lead Pencil Studeio
Fri 9/16/2022 11:05 AM | Conley, Nick <Nick.Conley@soundtransit.org> | P22-09-323 ST-Rockwell SCADA restore test cancelled | Cancellation | P22-09-323 ST-Rockwell SCADA restore test cancelled - ST Network Support team is unable to perform the necessary work to the network |  |  |  | ST - Cancelled | ST-Rockwel
Fri 9/16/2022 6:58 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | P22-09-222 routine dynamic testing has been cancelled for tonight | Cancellation | P22-09-222 routine dynamic testing has been cancelled for tonight, 9/16, due to lack of operator |  |  |  | KCM - Cancelled | Siemens
Sat 9/17/2022 4:49 AM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-09-201 non rev light repair and access to electrical rooms | Cancellation | P22-09-201 had a required EIC last night (Facilities) and I would not open it without the EIC |  |  |  | KCM - Cancelled | Absher
Mon 9/19/2022 9:51 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-09-233 Rail Grinding MLK | Emergency | P22-09-233 EMERGENCY PERMIT - ARM Embedded Grinding |  |  |  | KCM/Contractor - Requested | KCM/ARM
Mon 9/19/2022 12:01 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-09-331 Siemens burn-in is cancelled 9/19 , 9/20 & 9/21 | Cancellation | Permit P22-09-331 Siemens burn-in is cancelled 9/19 , 9/20 & 9/21 |  |  |  | Contractor - Cancelled | Siemens
Monday, September 19, 2022 12:28 PM | claire.ashton@soundtransit.org | P22-09-301 cancelled Test of the PA System Announcements- UWS | Cancellation | P22-09-301 cancelled - Ahmed decided to wait until issues with FACP at the site are resolved |  |  |  | ST - Cancelled | ST
Mon 9/19/2022 1:11 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-09-338 Emergency Permit - EMERGENCY WORK- N09 TPSS RECTIFER REQUEST | Emergency | P22-09-338 Emergency Permit - EMERGENCY WORK- N09 TPSS RECTIFER REQUEST |  |  |  | KCM/Contractor - Requested | KCM/MEC
Mon 9/19/2022 1:27 PM | Tam Tran <mysticdblegend@yahoo.com> | Permit # P22-09-306 - Cancelled, PowerStudies Inc. Collect Electrical Equipment Data- ALS | Cancellation | Permit # P22-09-306 - Cancelled, work completed early |  |  |  | Contractor - Cancelled | Power Studies Inc.
Tue 9/20/2022 11:11 PM | Justin Dayton <wildlifedayton@hotmail.com> | #P22-09-325 Bird Control- IDS & CHS Permit | Cancellation | #P22-09-325 Bird Control- IDS & CHS Permit, staffing issues |  |  |  | Contractor - Cancelled | Innovative Wildlife Solutions
Wed 9/21/2022 12:56 AM | Jacobs, Laurie (KCRail) <Laurie.Jacobs-KCRail@soundtransit.org> | P22-09-329 Siemens cancelled due to lack of supervisor staffing | Cancellation | P22-09-329 Siemens cancelled due to lack of supervisor staffing |  |  |  | KCM - Cancelled | Siemens
Wed 9/21/2022 2:09 PM | Timothy Ramage <tim.ramage@convergint.com> | Permit P22-09-314 - Remove and replace Fire/intrusion system for Othello, Walden, Stadium Signal Houses and Bungalows - Complete | Cancelled | Permit P22-09-314 - Complete, 9/22 and 9/23 not needed |  |  |  | Contractor - Cancelled | Convergint
Wed 9/21/2022 4:41 PM | Adam, Christopher M. <CMAdam@cce-inc.com> | Please cancel Permit # P22-09-322 for window tinting @ Roosevelt Station. | Cancelled | Please cancel Permit # P22-09-322 for window tinting @ Roosevelt Station. Scissor lift is needed for the work, delivery of lift was not accomplished. |  |  |  | Contractor - Cancelled | Centennial
Thu 9/22/2022 6:13 AM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | P22-09-331 Siemens burn in has been cancelled per contractor for 9/22/2022 | Cancelled | P22-09-331 Siemens burn in has been cancelled per contractor for 9/22/2022 |  |  |  | Contractor - Cancelled | Siemens
Thu 9/22/2022 11:30 AM | Hinga, Titus (KCRail) <Titus.Hinga-KCRail@soundtransit.org> | Permit P22-09-317 - Fiber Pull into OMFE Yard Manholes, Comm Room and TPSS, Cancelled | Cancelled | Permit P22-09-317 - Fiber Pull into OMFE Yard Manholes, Comm Room and TPSS, Cancelled |  |  |  | Contractor - Cancelled | MEC
Mon 9/26/2022 4:25 AM | Schubert, Jacob (KCRail) <jacob.schubert-kcrail@soundtransit.org> | Permit P-22-09-432 on 9/26/22, DAS Infrastructure Troubleshoot- WLS | Cancelled - No Show | Permit P-22-09-432 on 9/26/22, contractor no show |  |  |  | KCM - Cancelled | Mobilitie
Tue 9/27/2022 1:25 PM | Necessary, Jason W. <Jason.Necessary@wsp.com> | P22-09-403: Field Measurements of Fans- IDS, PSS, USS, and WLS Fan Rooms | Cancelled | Cancel Permit P22-09-403: Work Complete. |  |  |  | Contractor - Cancelled | WSP
Tue 9/27/2022 6:17 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | P22-09-426 Siemens burn in cancelled | Cancelled | Siemens burn in under permit P22-09-426 has been cancelled per contractor for 9/27/22 |  |  |  | Contractor - Cancelled | Siemens
Thu 9/29/2022 12:18 AM | Jacobs, Laurie (KCRail) <Laurie.Jacobs-KCRail@soundtransit.org> | P22-09-425 Siemens routine dynanic cancelled | Cancelled | Due to the potential of de-energized wire overlapping into the test block, Siemens testing has been canceled tonight. 09-29. |  |  |  | KCM - Cancelled | N/A
Wednesday, September 28, 2022 5:35 PM | Pinak Gupte <PGupte@mobilitie.com | P22-09-432 Mobilitie DAS Troubleshooting - Westlake Station cancel the permit for the remainder of the week. | Cancelled | P22-09-432 Mobilitie DAS Troubleshooting - Westlake Station cancel the permit for the remainder of the week. |  |  |  | Contractor - Cancelled | Mobilitie
Thursday, September 29, 2022 10:36 PM | Marian Stec <mstec@aegion.com> | P22-09-402 cancelled - Structure Stray Current Junction Box Testing Monitoring, Northgate Extension | Cancelled | P22-09-402 cancelled due to an unexpected development on another project |  |  |  | Contractor - Cancelled | Corrpro
Fri 9/30/2022 2:35 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens burn in under permit P22-09-426 has been cancelled per contractor for 9/30/22 | Cancelled | Siemens burn in under permit P22-09-426 has been cancelled per contractor for 9/30/22 |  |  |  | Contractor - Cancelled | Siemens
Mon 10/3/2022 8:44 AM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens burn in on 10/1 under Permit 426 was cancelled per contractor | Cancelled | Siemens burn in under permit P22-09-426 has been cancelled per contractor for 10/1/22 |  |  |  | Contractor - Cancelled | Siemens
Tue 10/4/2022 10:31 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-10-129 Emergency Permit - SODO Comm Cabinet | Emergency | P22-10-129 Emergency Permit - SODO Comm Cabinet |  |  |  | KCM/Contractor - Requested | Mechanical Services
Tue 10/4/2022 5:11 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens burn in under permit P22-10-114 has been cancelled per contractor for 10/04. | Cancelled | Siemens burn in under permit 114 has been cancelled per contractor for 10/04. |  |  |  | Contractor - Cancelled | Siemens
Tue 10/4/2022 5:14 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens routine testing under permit P22-10-115 is cancelled per contractor for 10/05 (Tue night/Wed morning). | Cancelled | Siemens routine testing under permit P22-10-115 is cancelled per contractor for 10/05 (Tue night/Wed morning). |  |  |  | Contractor - Cancelled | Siemens
Wed 10/5/2022 5:38 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens routine testing under permit P22-10-115 for 10/6 (Wed night/Thu morning) has been cancelled per contractor. | Cancelled | Siemens routine testing under permit P22-10-115 for 10/6 (Wed night/Thu morning) has been cancelled per contractor. |  |  |  | Contractor - Cancelled | Siemens
Thu 10/6/2022 10:10 PM | Pinak Gupte <PGupte@mobilitie.com> | P22-10-120 updated rev-1 Mobilitie DAS Troubleshooting - Westlake Station - Track Access Submittal - 10.03.2022 | Cancelled | P22-10-120 updated rev-1 Mobilitie DAS Troubleshooting - Westlake Station - Track Access Submittal - 10.03.2022 |  |  |  | Contractor - Cancelled | Mobilitie
Sat 10/8/2022 7:11 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Siemens burn in under permit P22-10-114 has been cancelled per contractor for 10/8/22 | Cancelled | Siemens burn in under permit P22-10-114 has been cancelled per contractor for 10/8/22 |  |  |  | Contractor - Cancelled | Siemens
Tue 10/11/2022 7:40 AM | LaZerte, Adam (KCRail) <Adam.LaZerte-KCRail@soundtransit.org> | P22-10-239 CTS Vault Investigation & Pull String Install- E3 Busway 239 canceled for two days | Cancelled | P22-10-239 CTS Vault Investigation & Pull String Install- E3 Busway 239 canceled for two days |  |  |  | Contractor - Cancelled | CTS
Tue 10/11/2022 10:56 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-10-226, Siemens Burn-In train has been cancelled per contractor for this evening, Tuesday, October 11th. | Cancelled | Permit P22-10-226, Siemens Burn-In train has been cancelled per contractor for this evening, Tuesday, October 11th. |  |  |  | Contractor - Cancelled | Siemens
Tue 10/11/2022 3:02 PM | Rockwell, Ed | P22-10-238 and P22-10-239 CTS Fiber Pull - Cancel for this week | Cancelled | P22-10-239 Central Link Fiber Project needs to cancel the approved permit for the week of 10/10/2022 |  |  |  | Contractor - Cancelled | CTS
Wed 10/12/2022 2:21 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-10-240 Emergency Permit Data Log recovery | Emergency | P22-10-240 Emergency Permit Request TPSS N07 and TPSS N11 Data Log recovery |  |  |  | KCM/ST - Requested | KCM/ST
Wed 10/12/2022 2:21:00 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-10-241 Emergency Permit ROW visual Inspection North of N10-TPSS to the end of line | Emergency | P22-10-241 Emergency Permit Request ROW visual Inspection North of N10-TPSS to the end of line |  |  |  | KCM/ST - Requested | KCM/MEC
Fri 10/14/2022 7:42 AM | Flocco III, Joseph R. <J.FloccoIII@wsp.com> | Cancel Permit # P22-10-230 | Cancelled | Cancel Permit # P22-10-230 - Lighting measurements in the DSTT |  |  |  | Contractor - Cancelled | WSP
Fri 10/14/2022 3:07 PM | Rockwell, Ed | P22-10-333 and P22-10-334 - Cancel for Next Week | Cancelled | Cancel Permit P22-10-333 and P-10-334 for next week. Both related to Central Link Fiber Project |  |  |  | Contractor - Cancelled | CTS
Fri 10/14/2022 3:17 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org> | P22-10-242 EMERGENCY Permit and Workplan: Cars 223 and 258 IDS Platform Measurements | Emergency | An emergency permit has been issued. Permit P22-10-242, Vehicle to Platform Measurements. |  |  |  | ST - Requested | ST
Fri 10/14/2022 3:36 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit 225, Siemens Groundborne Vibration testing has been cancelled per contractor for this evening, Friday, October 14th | Cancelled | The available Groundborne Vibration testing resources will now support the above mentioned emergency permit (P22-10-242) |  |  |  | KCM - Cancelled | Siemens
Mon 10/17/2022 10:11 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P22-10-324 Siemens Burn-In Train | Cancelled | Permit 324, Siemens Burn-In train has been cancelled per contractor for this evening, Monday, Oct 17th |  |  |  | Contractor - Cancelled | Siemens
Mon 10/17/2022 1:04 PM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P22-10-321 PIMS SIT with SCADA TCS and GTFS 10-18-2022 | Cancelled | P22-10-321 PIMS SIT with SCADA TCS and GTFS 10-18-2022, first night only cancelled |  |  |  | Contractor - Cancelled | Wabtec
Mon 10/17/2022 8:50 PM | Jacobs, Laurie (KCRail) <Laurie.Jacobs-KCRail@soundtransit.org> | P22-10-325 Routine Dynamic XLD Staffing | Cancelled | P22-10-325 Siemens Routine Dynamic XLD due to Staffing |  |  |  | KCM - Cancelled | Siemens
Wed 10/19/2022 12:15 PM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P22-10-321 PIMS SIT with SCADA TCS and GTFS 10/20 and 10/21 | Cancelled | no additional testing on this permit for Thursday 10/20 or Friday 10/21. We successfully completed this week’s objectives in the early morning today. |  |  |  | Contractor - Cancelled | Wabtec
Mon 10/24/2022 7:04 AM | LaZerte, Adam (KCRail) <Adam.LaZerte-KCRail@soundtransit.org> | Permit 22-10-414 canceled for today | Cancelled | The Fiber Guys will not be on site this morning at OMFE but will be on site tomorrow morning at 0800 |  |  |  | Contractor - Cancelled | MEC
Wed 10/26/2022 12:27 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit 22-10-424 canceled for 10/27 thru 10/29 | Cancelled | Permit 424, Siemens Routine Dynamic has been cancelled per contractor for Thursday morning, October 27th thru Saturday morning, October 29th. |  |  |  | Contractor - Cancelled | Siemens
Thu 10/27/2022 2:38 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org> | P22-10-441 Emergency Request for Siemens LRV Groundborne testing | Emergency | P22-10-441 Emergency Request for Siemens LRV Groundborne testing |  |  |  | ST - Requested | Siemens
Fri 10/28/2022 5:43 AM | Mark Swint <Mark.Swint@formacc.com> | Cancel permit P22-10-436 for fri 10-28 (Fare Pay Zone Project – Conduit Layout & Electrical Rough-in Westlake Station | Cancelled | The contractors have moved to 4 - 10s per week, please cancel the Work for tonight. |  |  |  | Contractor - Cancelled | Forma
Fri 10/28/2022 1:55 PM | Nicholas Harris <nharris@albireoenergy.com> | Cancellation for Permit #P22-10-514: No FA1 Support | Cancelled | PAC Firmware Update- NGS and Maple Leaf Portal - cancel the attached permit due to FA1 support not being provided |  |  |  | Contractor - Cancelled | Alvireo Energy
Mon 10/31/2022 7:31 AM | Conley, Nick <Nick.Conley@soundtransit.org> | P22-10-524 Phase 4 Rockwell SCADA Restore Test - BMS Cloud - Cancelled due to network issue | Cancelled | The BMS Cloud restore environment continues to have connectivity issues. Please cancel this Phase 4 (Cloud BMS Restore Test) permit for 11/1 – 11/3. |  |  |  | Contractor - Cancelled | Rockwell
Tuesday, November 1, 2022 6:39 AM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P22-10-516 PIMS SIT with SCADA TCS and GTFS 11-01-2022 | Cancelled | PIMS Milestone 4 Systems Integration Tests with SCADA TCS and GTFS |  |  |  | Contractor - Cancelled | Wabtec Corporation/ARINC
Tues 11/1/2022 8:11 AM | Aayat.Kazi <Aayat.Kazi@masselec.com> | P22-10-540 Cancellation | Cancelled | Live Wire Testing |  |  |  | Contractor - Cancelled | Mass Elec
Wednesday, November 02, 2022 3:31 AM | John.Landis@masselec.com | P22-10-519 Udist KCM permit 10-31-22 | Cancelled | Site Visit for Damaged Fiber Repair- N07 MVSS Room N07B329 |  |  |  | Contractor - Cancelled | Mass Elec
Fri 11/4/2022 3:26 AM | Brockett, Glenn (KCRail) <Glenn.Brockett-KCRail@soundtransit.org> | P22-10-531 no show | No Show, Cancelled | Siemen’s vibration testing was a no show this evening |  |  |  | No Show, Cancelled | Siemens
Fri 11/4/2022 11:54 AM | Mark Swint <Mark.Swint@formacc.com> | P22-10-526 cancellation | Cancelled | Cancel the remainder of this permit. No work this evening 11-4 |  |  |  | Contractor - Cancelled | Formacc
Fri 11/4/2022 2:00 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit 531, Siemens Groundborne Vibration testing has been cancelled per contractor for this evening, Friday, Nov 4th | Cancelled | P22-10-531, Siemens Groundborne Vibration testing cancelled for evening of Nov 4th |  |  |  | Contractor - Cancelled | Siemens
Mon 11/7/2022 7:27 AM | Sneen, Scott <ssneen@railworks.com> | CANCEL Permit #P22-11-134 - Panel Lift – Royal Brougham | Cancelled | Please cancel Permit # P22-11-134 for all requested dates due to postponement of the associated activities/project |  |  |  | Contractor - Cancelled | Railworks
Mon 11/7/2022 8:38 AM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P22-11-138 PIMS SIT with SCADA TCS and GTFS 11-08-2022 Cancelled | Cancelled | PIMS Milestone 4 Systems Integration Tests with SCADA TCS and GTFS |  |  |  | Contractor - Cancelled | Collins
Tue 11/8/2022 5:28 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P22-11-122 & P22-11-123 Siemens Routine Dynamic and Burn in cancelled | Cancelled | Permit 122, Siemens Routine Dynamic cancelled for this evening, Tuesday, Nov 8th. Permit 123, Siemens Burn-In has been cancelled also 8th thru Saturday, Nov 12th |  |  |  | Contractor - Cancelled | Siemens
Thu 11/10/2022 11:16 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-11-132 LATE/ACCEPTED SPP Onboard Noise Measurements | Cancelled | P22-11-132 SPP Onboard Noise Measurements - last day cancelled |  |  |  | Contractor - Cancelled | Spy Pond
Thu 11/10/2022 2:16 PM | Salvador Benitez <salvador.benitezjr@c3mpowersystems.com> | Track Access Permit #P22-11-239 Cancellation - C3M Replace Insulators | Cancelled | Track Access Permit #P22-11-239 Cancellation - C3M Replace Section Insulators - OMFE VM Shop |  |  |  | Contractor - Cancelled | C3M
Fri 11/11/2022 1:05 PM | Nicholas Harris <nharris@albireoenergy.com> | P22-11-222 Track Access Permit for University Street Station- 11/16/22 - OCS Disconnect - PLC Control Updates | Cancelled | I will be cancelling this permit for 11/16/22. The option of utilizing the 14th and 15th unfortunately will not work for our team. |  |  |  | Contractor - Cancelled | Albireo Energy
Mon 11/14/2022 8:55 AM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org> | P22-10-242 EMERGENCY Permit and Workplan: Cars 223 and 258 IDS Platform Measurements | Emergency | P22-10-242 emergency permit to take cars 223 and 258 out to IDS Southbound tonight for door-to-platform measurements. |  |  |  | Emergency - ST | Emraj Sidhu, ST
Tue 11/15/2022 9:50 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit 225, Siemens Burn-In train has been cancelled per contractor for this evening, Tuesday, November, 15th 2022 | Cancelled | P22-11-225, Siemens Burn-In train has been cancelled per contractor for this evening, Tuesday, November, 15th 2022 |  |  |  | Contractor - Cancelled | Siemens
Fri 11/18/2022 7:15 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-11-247 EMERGENCY PERMIT - Columbia City Station Paver Repair | Emergency | P22-11-247 EMERGENCY PERMIT - Columbia City Station Paver Repair |  |  |  | Emergency - ST/Contractor | Waters Construction
Fri 11/18/2022 12:24 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-11-225, Siemens Burn-In train has been cancelled this evening, Friday, November 18th & Saturday, November 19th per contractor | Cancelled | Permit P22-11-225, Siemens Burn-In train has been cancelled this evening, Friday, November 18th & Saturday, November 19th per contractor |  |  |  | Contractor - Cancelled | Siemens
Fri 11/18/2022 12:51 PM | Anita Phonexayphova <Anita.Phonexayphova@gly.com> | Cancel Permit #P22-11-309 related to U-District Transfer Beam Investigation work week of 11/21 – 11/23 (Survey/Chipping of Concrete Girder- UDS TOD Lot) | Cancelled | Cancel Permit #P22-11-309 related to U-District Transfer Beam Investigation work week of 11/21 – 11/23. |  |  |  | Contractor - Cancelled | GLY Construction, BRH, Snyder
Fri 11/18/2022 1:33 PM | Anita Phonexayphova <Anita.Phonexayphova@gly.com> | cancel Permit #P22-11-437 related to U-District Transfer Beam Investigation work week of 11/28 – 12/02 (Survey/Chipping of Concrete Girder- UDS TOD Lot) | Cancelled | Cancel Permit #P22-11-439 related to U-District Transfer Beam Investigation work week of 11/28 – 12/02. |  |  |  | Contractor - Cancelled | GLY Construction, BRH, Snyder
Fri 11/18/2022 2:28 PM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-11-248 Emergency Permit: Mobilitie: University of Washington Station and NB bore of University of Washington : 11/19/22 no power down | Emergency | P22-11-248 Emergency Permit: Mobilitie: University of Washington Station and NB bore of University of Washington : 11/19/22 no power down |  |  |  | Emergency - Contractor | Mobilitie
Sun 11/20/2022 8:26 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Permit P22-11-312, Siemens Burn-In train has been cancelled per contractor for Monday, November 21st thru Wednesday, November | Cancelled | Permit P22-11-312, Siemens Burn-In train has been cancelled per contractor for Monday, November 21st thru Wednesday, November |  |  |  | Contractor - Cancelled | Siemens
Tue 11/22/2022 9:09 AM | Wheatley, Carl IMS <carl.wheatley@collins.com> | Cancelled P22-11-417 PIMS SIT with SCADA TCS and GTFS 11-29-202 | Cancelled | This track access request/permit (P22-11-417) can be cancelled. There are IT infrastructure issues blocking work on this permit at this time |  |  |  | Contractor - Cancelled | Wabtec Corporation/ARINC
Tue 11/22/2022 12:46 PM | Wheatley, Carl IMS <carl.wheatley@collins.com> | P22-11-416 PIMS Milestone 4 DIO with PAVMS for Field Integration Testing | Cancelled | This permit can be cancelled. The time allotted to support this test is insufficient. |  |  |  | Contractor - Cancelled | Wabtec Corporation
Wed 11/23/2022 10:34 AM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | P22-11-410 OCS Live Wire Testing Cancelled due to an ongoing issue with the Test LRV | Cancelled | Cancelled due to an ongoing issue with the Test LRV that needs to be addressed we will be canceling Live Wire testing on 11/28/22 |  |  |  | Contractor - Cancelled | MEC
Tue 11/29/2022 9:33 AM | John Bearden <bearden@gravitec.com> | Cancellation of Permit # P22-11-404, due to staffing, Gravitec fall protection inspection | Cancelled | Cancellation of Permit # P22-11-404, due to staffing, Gravitec fall protection inspection |  |  |  | Contractor - Cancelled | Gravitec
Tue 11/29/2022 9:32 PM | Nicholas Harris <nharris@albireoenergy.com> | P22-11-431 Albireo Energy will be canceling their scheduled permit work for tonight, 11/29/22, due to weather conditions | Cancelled | P22-11-431 Albireo Energy will be canceling OCS Disconnect Switches- PLC Control Updates- USS work for tonight, 11/29/22, due to weather conditions |  |  |  | Contractor - Cancelled | Albireo Energy
Wed 11/30/2022 7:32 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | Permit P22-11-410 E Link live wire testing for 11/30 has been canceled per contractor. | Cancelled | Permit P22-11-410 E Link live wire testing for 11/30 has been canceled per contractor. |  |  |  | Contractor - Cancelled | Mass Elec
Wed 11/30/2022 8:20 PM | Nicholas Harris <nharris@albireoenergy.com> | P22-11-431 Albireo Energy will be canceling their scheduled permit work for tonight, 11/30/22, due to foreseeable overnight weather conditions | Cancelled | P22-11-431 Albireo Energy will be canceling their scheduled permit work for tonight, 11/30/22, due to foreseeable overnight weather conditions |  |  |  | Contractor - Cancelled | Albireo Energy
Thu 12/1/2022 4:50 AM | Klingelhoffer, Edward <Edward.Klingelhoffer-KCRail@soundtransit.org> | P22-11-410 No show for 11/30/22 – 12/01/2022. Live Wire Testing w/4-car KI, leaving from OMFE | No show | P22-11-410 No show for 11/30/22 – 12/01/2022. Signal Department not notified of cancellation. |  |  |  | Contractor - No show | Mass Elec
Thu 12/1/2022 4:36 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | P22-11-422 Siemens burn-in has been canceled for tonight and for the remainder of this permit cycle. | Cancelled | P22-11-422 Siemens burn-in has been canceled for tonight and for the remainder of this permit cycle. |  |  |  | Contractor - Cancelled | Siemens
Mon 12/5/2022 8:52 AM | Miller, Bridget <Bridget.Miller@soundtransit.org> | P22-12-105 Cancelled. Network Gear Installation- OMF 3rd Floor. Work completed | Cancelled | P22-12-105 Cancelled. We completed our work this week and won’t need this permit. |  |  |  | Contractor - Cancelled | Sound Transit & DaTec
Mon 12/5/2022 3:54 PM | Johnothon.Humphrey <Johnothon.Humphrey@masselec.com> | Permit P22-12-106 cancelled for the evening of 12/5/22, we will resume testing on 12/6/22. Live Wire Testing w/4-car KI, leaving from OMFE. | Cancelled | Permit P22-12-106 cancelled for the evening of 12/5/22, we will resume testing on 12/6/22. |  |  |  | Contractor - Cancelled | Mass Elec
Mon 12/5/2022 6:17 PM | Routh, Nicholas (KCRail) <Nicholas.Routh-KCRail@soundtransit.org> | MEC informed me that permit P22-12-112 E Link signals testing is canceled starting 12/6 thru 12/9. | Cancelled | MEC informed me that permit P22-12-112 E Link signals testing is canceled starting 12/6 thru 12/9. |  |  |  | Contractor - Cancelled | Mass Elec
Fri 12/9/2022 10:32 AM | Scott.Glen <sglen@masselec.com> | Cancel 12/14/2022 from permit P22-12-202 splicing concrete replacement CHS and Pine St. | Cancelled | Cancel 12/14/2022 from permit P22-12-202 as we will not have supervision available to support. 12/12/22, 12/13/22, and 12/14/22 are still planned to be used. |  |  |  | Contractor - Cancelled | Mass Elec
Fri 12/9/2022 10:52 AM | Scott.Glen <sglen@masselec.com> | Cancel permit P22-12-130. Junction box replacement at NGS interlocking. | Cancelled | Cancel permit P22-12-130. Rescheduled due to weather from a previous week and we are unable to support the work under the new date. |  |  |  | Contractor - Cancelled | Mass Elec
Fri 12/16/2022 7:05 AM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | Siemens permits P22-12-216,217 & 218 have all been cancelled per contractor for this evening, Friday, December 16th | Cancelled | Siemens permits P22-12-216,217 & 218 have all been cancelled per contractor for this evening, Friday, December 16th |  |  |  | Contractor - Cancelled | Siemens
Mon 12/19/2022 4:08 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-334 Mobilitie cancelling tonight’s work for 12/20/22 University of Washington Station and NB bore of University of Washington | Cancelled | P22-12-334 Mobilitie cancelling tonight’s work for 12/20/22 from 0001 – 0400 due to safety reasons for cold temperatures and possible ice trains running |  |  |  | Contractor - Cancelled | Mobilitie
Mon 12/19/2022 4:09 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-333 LATE/ACCEPTED Mobilitie: Beacon Hill Station and NB and SB bore of Beacon Hill : 12/20/22 | Cancelled | P22-12-333 Mobilitie cancelling tonight’s work for 12/20/22 from 0001 – 0400 due to safety reasons for cold temperatures and possible ice trains running |  |  |  | Contractor - Cancelled | Mobilitie
Mon 12/19/2022 7:51 PM | Garraway, Robert (KCRail) <Robert.Garraway-KCRail@soundtransit.org> | P22-12-301 splicing concrete replacement CHS and Pine St. canceled for 12/20/22 | Cancelled | P22-12-301 canceled for 12/20/22 due to “All hands on deck Level 3 snow response” at 10pm. |  |  |  | KCM - Cancelled | Mass Elec
Tue 12/20/2022 2:30 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-333 LATE/ACCEPTED Mobilitie: Beacon Hill Station and NB and SB bore of Beacon Hill : 12/21/22 | Cancelled | P22-12-333 LATE/ACCEPTED Mobilitie: Beacon Hill Station and NB and SB bore of Beacon Hill : 12/21/22 |  |  |  | Contractor - Cancelled | Mobilitie
Tue 12/20/2022 2:30 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-334 Mobilitie cancelling tonight’s work for 12/21/22 University of Washington Station and NB bore of University of Washington | Cancelled | P22-12-334 Mobilitie cancelling tonight’s work for 12/21/22 from 0001 – 0400 due to safety reasons for cold temperatures and possible ice trains running |  |  |  | Contractor - Cancelled | Mobilitie
Wed 12/21/2022 8:18 AM | Keolker, Nick (KCRail) <Nick.Keolker-KCRail@soundtransit.org> | P22-12-344 Provac Cleaning, Jetting & CCTV Drainpipes - Othello and Walden interlocking cancelled tonight due to weather. | Cancelled | P22-12-344 Provac Cleaning, Jetting & CCTV Drainpipes - Othello and Walden interlocking cancelled tonight due to weather. |  |  |  | Contractor - Cancelled | Provac
Thu 12/22/2022 6:48 AM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-317 Wabtec PIMS FIT DIO with PAVMS 12-19-2022 | Cancelled | Due to sick call outs we don’t have enough staff on tonight to support any work in the field and will have to cancel this permit. |  |  |  | KCM - Cancelled | Wabtec
Thu 12/22/2022 1:45 PM | James, Kavin (KCRail) <Kavin.James-KCRail@soundtransit.org> | P22-12-323, Siemens Routine Dynamic has been cancelled due to inclement weather. | Cancelled | P22-12-323, Siemens Routine Dynamic has been cancelled due to inclement weather. Siemens contractor has been notified. |  |  |  | KCM - Cancelled | Siemens
Fri 12/23/2022 8:16 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-334 Mobilitie cancelling tonight’s work for 12/24/22 University of Washington Station and NB bore of University of Washington | Cancelled | P22-12-334 Mobilitie cancelling tonight’s work for 12/24/22 University of Washington Station and NB bore of University of Washington |  |  |  | Contractor - Cancelled | Mobilitie
Fri 12/23/2022 8:16 AM | Griffiths, Lauren (KCRail) <lauren.griffiths-kcrail@soundtransit.org>; on behalf of; Link Track Access <linktrackaccess@soundtransit.org> | P22-12-333 LATE/ACCEPTED Mobilitie: Beacon Hill Station and NB and SB bore of Beacon Hill : 12/24/22 | Cancelled | P22-12-333 LATE/ACCEPTED Mobilitie: Beacon Hill Station and NB and SB bore of Beacon Hill : 12/24/22 |  |  |  | Contractor - Cancelled | Mobilitie
Tue 12/27/2022 5:18 PM | Morgan, Kathy (KCRail) <Kathy.Morgan-KCRail@soundtransit.org> | P22-12-413 Columbia City Station Tile repair - EIC no show | EIC No Show | P22-12-413 Columbia City Station Tile repair - EIC no show |  |  |  | KCM - Cancelled | Waters Construction

## Cancelled requests
PERMIT REQUESTS PREPARED, REVIEWED AND DISCUSSED BUT CANCELLED PRIOR TO ISSUE - DECEMBER 2022.
Contractor | Permit # | ST PM | Reason |  |  | Start | End | Location | Description | Power Down |  | Support
100 series
Gravitec Systems Fritz Kraft 360 981 4905 | P22-12-101 | Joe Forgette 206 255 7680 | KCM CANCELLED, no power down available | 44901 | 44904 | 0001 | 0600 | Angle Lake plaza level roofs and station roofs, TIBS mezzanine and station roofs, and UWS level B4 | Annual inspection and light maintenance of fall protection systems, work involves walking and observing the conditions of all systems, photo documentation, and light maintenance (replacing cotter pins, tighten fasteners, etc.). OCS will need to be de-energized when inspecting the systems on the roof levels at ALS and TIBS, and the systems on level B4 at UWS KCM EIC and support required. | YES - not available | N | Facilities, Traction Power
Gravitec Systems Fritz Kraft 360 981 4905 | P22-12-102 | Joe Forgette 206 255 7680 | CANCELLED, per Contractor | 44900 | 44904 | 0900 | 1700 | CHS - All roof levels, mezzanines and basement | Annual inspection and light maintenance of fall protection systems, work involves walking and observing the conditions of all systems, photo documentation, and light maintenance (replacing cotter pins, tighten fasteners, etc.). KCM EIC required. | N | N | Facilities
WSP David Moeller 850 910 3934 | P22-12-103 | Minna Yan 206 553 3722 | KCM CANCELLED- no support available | 12/05/22 12/05/22 12/06/22 | 12/05/22 12/06/22 12/07/22 | 0001 2300 2000 | 0400 | DSTT tunnel south of WLS, WLS and USS stations, and the stairs to Benaroya Hall (USS) and to the monorail (WLS). | Lighting measurement and assessment require the shut off of the breaker/power to select circuits to allow for measurements of the emergency lighting system and to confirm if lighting levels are adequate. Will need to de-energize escalators during non-revenue to measure light on adjacent stairs (normal power only to escalators). KCM EIC required. | N | N | Facilities
GLY Construction/BRH/Snyder Brian Sandall (425) 765-7114 | P22-12-113 | Kristin Hoffman 206 650 4474 | KCM CANCELLED- Roof is still red-tagged. | 44900 | 44904 | 0700 | 1700 | UDS N & S Head house Rooftop | Roof Demo/Survey. Surveying x/y/z coordinates of existing column stub-outs for future connection. Demo/patching of isolated portion of roof assembly will be required at North Head House roof where (1) column connection is buried under existing tie-off davit. KCM EIC required. | N | N | Facilities
Sound Transit Tim Thew 425-516-9779 | P22-12-119 | Nick Conley 832-860-9300 | KCM CANCELLED- Conflicts with Vent Mode Testing | 44901 | 44903 | 2330 | 0400 | OMF 3rd Floor Datacenter | Disaster Recovery Cloud Backup Restore Test for Rockwell Collins BMS. Rockwell BMS system will be temporarily failed over to a separate recovery environment for validation. There may be brief disruptions to BMS visibility while this work is performed. KCM EIC required. | N | N | SCADA
ST OT Tyler Lentz 425-480-1495 | P22-12-126 | Heather Pederson 720-937-1428 | KCM CANCELLED, no support | 44901 | 44901 | 0100 | 0400 | C37 (SeaTac/Airport Sub), S01(Angle Lake) (TPSS) | Complete Transfer Trip testing from C37 to S01 with MOD’s open at S01. ST will connect laptop during testing and monitor logic. MOD’s at S01 will be reclosed at the end of testing, before passenger service resumes. For any tripped breakers, Traction Power will notify the LCC duty Chief to close the breakers via SCADA. Traction Power will then verify with the LCC that the breakers are closed in the field. KCM EIC required. | N | N | Traction Power
ST/ProVac/Schindler Chris Echevarria 253-606-7739 | P22-12-127 | Carlos Trujillo 206-465-3863 | CANCELLED, per Contractor | 44901 | 44901 | 0100 | 0400 | North End of University Street Station platform/Elevator pit | Debris Removal for Elevator #506 Jack Replacement Project. Pro-Vac will drive their Vac truck next to the platform of University Street Station. The elevator jack will be removed so Pro-Vac can remove materials 50-60ft below the pit floor. KCM EIC and support required. | YES | N | Facilities, Traction Power
200 series
Woojin IS America Junsuk Jeong (626) 385-1804 | P22-12-203 | Eva Relano 206 398 5471 | CANCELLED, per Contractor | 44907 | 44911 | 0800 | 1700 | OMF East- Shop | Electronic System Investigation of ST1 LRV. Team will investigate – functions of on-board communication system; TOD screen design; back-office software operations; investigation on the on-board LonWorks network; wiring path; design and dimension of existing system equipment; overall vehicle structure. Coordinate all activities with Vehicle Maintenance. KCM support required. | YES- In yard/shop | N | Vehicle Maintenance, Traction Power
ARM/Plasser American Jeff Schweisthal 321 698 3024 | P22-12-208 | Eric Gatliff 206 655 2209 | CANCELLED- Per Contractor, Work is done for the year | 44907 | 44913 | 0130 0700 | 0430 1400 | OMF Northend Storage Track 1 or NGS Maintenance Track | Demob Milling Machine - Option 1: OMFC Milling Machine will be unloaded between Maintenance Facility and Track S-1. Option 2: Travel to Northgate Maintenance track from OMF Mill Machine will travel to the Northgate maintenance track during non-revenue hours with the crane located on 1st Ave NE near NE 95th St. The door to the maintenance track will need to be opened for crane access from roadway with milling carts craned onto waiting trailers on roadway. KCM EIC and support required. Coordinate with Vehicle Maintenance, 24-advance notice to VM. | YES - in yard (S1-S3) | N | Track, Traction Power, Vehicle Maintenance
Sound Transit Tim Thew 425-516-9779 | P22-12-213 | Nick Conley 832-860-9300 | CANCELLED, per Contractor | 44908 | 44910 | 2330 | 0400 | OMF 3rd Floor Datacenter | Disaster Recovery Cloud Backup Restore Test for Rockwell Collins TCS. Failover to restored TCS Rockwell Collins Servers for validation testing, then failback to production. KCM EIC required. | N | N | SCADA
WSP David Moeller 850 910 3934 | P22-12-224 | Minna Yan 206 553 3722 | CANCELLED, per Contractor | 44908 | 44910 | 1000 | 1800 | IDS Station, Pioneer Station, University Station, Westlake Station, Pine Street Ventilation. (Electrical Rooms) | Visual-only inspections of lighting power equipment (panelboards, UPS, controls, etc.) entering electrical rooms and visually observing equipment only. KCM EIC required. | N | N | Facilities
Mass Electric Mike Rafferty 213-305-9489 | P22-12-226 | Ben Neeley 404 922 1930 | CANCELLED, Per Contractor | 44907 | 44908 | 0700 | 1530 | OMF-E to Construction side: City Hall Interlocking, Kirkland Wye, Kelsey Creek Interlocking | SIT 400 Series Signal Testing with 4-Car KI consist. KCM support required. Operations assistance required for Operator and Supervisor. Coordinate all activities with Vehicle Maintenance, VM unavailable beginning 1500. | N | N | Signals, Operations, Vehicle Maintenance
Mass Electric Keith Schlosser/Dan Myers 503-969-7969/253-208-5836 | P22-12-227 | Ben Neeley 404 922 1930 | CANCELLED, per KCM no support | 44907 | 44908 | 0030 | 0430 | N09 SCL Room and N09 TPSS & FCC Room | SCL Breaker Wiring. Install wiring from comm cabinet in the N09 TPSS room to the control cabinet in the N09 SCL room at the Roosevelt Station. Install relays in control cabinet in N09 SCL Room. Perform SCADA testing to verify control and indications of the SCL breaker. KCM EIC required. KCM support on standby. | N | N | Traction Power, SCADA (on standby if needed)
GLY Construction/BRH/Snyder Brian Sandall (425) 765-7114 | P22-12-229 | Kristin Hoffman 206 650 4474 | CANCELLED, per Contractor | 44907 | 44911 | 0700 | 1700 | UDS N & S Head house Rooftop | Roof Demo/Survey. Surveying x/y/z coordinates of existing column stub-outs for future connection. Demo/patching of isolated portion of roof assembly will be required at North Head House roof where (1) column connection is buried under existing tie-off davit. Sound Transit Facilities assistance for access. | N | N | ST Facilities
300 series
Western Ventures/Vet First Taus Casswell 253-686-1308 | P22-12-305 | Gita Monghate/Levi Young 206-903-7180 | CANCELLED, per Contractor & KCM discussion at 1 pm meeting - work not ready to move forward. | 44916 | 44917 | 0100 | 0400 | OMF- 4th Floor, 416 Room | HVAC Replacement - Install a Reverse Osmosis Filtration System in Rm. 416. This installation requires the shutdown of domestic cold water to allow for the final connection. The water shutdown will affect the whole building. KCM EIC required. | N | N | Facilities
ST/Intersection Kyle Ingram/John McNeeley 860 861 4174 | P22-12-309 | Heather Pedersen 720 937 1428 | CANCELLED, per Contractor | 12/19/22 12/20/22 | 12/19/22 12/23/22 | 1430 1700 | 2000 | WLS, UWS, Stadium, SeaTac, USS CHS Platforms, Mezzanines, Electrical Rooms & Panels | Installation of advertising displays and electrical panel verification. Will also start work to install stabilizer brackets at existing screens. KCM EIC required. | N | N | Facilities
Western Ventures/Vet First Taus Casswell 253-686-1308 | P22-12-310 | Gita Monghate/Levi Young 206-903-7180 | CANCELLED, per Contractor & KCM discussion at 1 pm meeting - work not ready to move forward. | 44916 | 44918 | 0500 | 1600 | OMF- 4th Floor, LCC and Server Room | HVAC Replacement - Reroute existing hydronic piping around the LCC. Once the new pipe run is installed, will need to shut down the heating loop on the 4th floor to make final connections. This will also shut down the 4th-floor heating for 4 hours. Doors must remain closed at all times. KCM EIC/EIS required. | N | N | Facilities
Lumenal Lighting Julien LeBeouf 425 758 3924 | P22-12-316 | Darren Simons 206 689 4643 | KCM CANCELLED, no support | 44914 | 44918 | 0700 | 1700 | Columbia City Station – Platform on West side of Tracks and the two bike rack areas. | Upgrade the LED fixtures. Need to shut down the lighting circuit. Will block off the work zone with 4 tall cones and caution tape to provide a safe workspace. A 19' scissor lift will be used in some areas. KCM EIC required. | N | N | Facilities
Sound Energy Systems Oliver King-Altrum 360 789 0481 | P22-12-318 | Ali Araghi 425 798 3838 | KCM CANCELLED, no support | 44914 | 44916 | 0700 | 1500 | OMF Building - DDC Control Panel Locations | DDC Control Panel Report. Identify the power panel and breaker number for each of the seven Control Panel (1,2,3,4,8,9,10) and any other CP for the DDC control system (if found). Generate a report with the findings. KCM EIC required. | N | N | Facilities
Centennial Contractors/City of SeaTac Rob Crossland 253-861-4714 | P22-12-320 | Heather Pedersen 720 937 1428 | CANCELLED, per Contractor | 44917 | 44917 | 0700 | 1600 | Electric Room G102, ground level underneath Seatac/Airport Station elevated platform | Final inspection of the new mechanical equipment and controls system updates, including the final electrical inspection. KCM EIC required. | N | N | Facilities
Mass Electric Mike Rafferty 213-305-9489 | P22-12-325 | Ben Neeley 404 922 1930 | CANCELLED, per Contractor | 44914 | 44916 | 0700 | 1530 | OMF-E to Construction side: City Hall Interlocking, Kirkland Wye, Kelsey Creek Interlocking | SIT 400 Series Signal Testing with 4-Car KI consist. KCM support required. Operations assistance required for Operator and Supervisor. Coordinate all activities with Vehicle Maintenance, VM unavailable beginning 1500. | N | N | Signals, Operations, Vehicle Maintenance
MEC/ST CMC Brent Lamoreaux 435-701-0006 | P22-12-330 | Ben Neeley 404 922 1930 | CANCELLED, per Contractor | 44914 | 44914 | 0001 | 0400 | IDS TCC Room, OMF 3rd Floor Comm Room | East Link TCN Tie-In Fiber Investigation. Verify Patch cables previously installed at IDS TCC room from JPS. Crew to use a fiber fault finder to shine light to validate fiber connections from JPS to IDS rack CR-13. KCM EIC required. | N | N | SCADA
Albireo Energy Jan Wiese-Hansen 425-786-6422 | P22-12-331 | Ahmed Idrees 206-903-0084 | KCM CANCELLED, no support | 44915 | 44917 | 2330 | 0330 | OMF, USS, platform level, room C05-H-602/C05.P12.DC05, and Comm Room (C5 5M02-NW). | Installing disconnect switches associated with the OCS. Complete installation of new PLC control modules, terminations to new PLC controls, and programming modifications to accommodate newly added equipment interface. Some testing will be required to verify signals back to the control system. KCM EIC and support required. | YES - not available | N | SCADA, Traction Power
WSP David Moeller 850 910 3934 | P22-12-332 | Minna Yan 206 553 3722 | CANCELLED, per Contractor | 12/19/22 12/19/22 12/20/22 | 12/19/22 12/20/22 12/21/22 | 0001 2300 2000 | 0400 | DSTT tunnel south of WLS, WLS and USS stations, and the stairs to Benaroya Hall (USS) and to the monorail (WLS). | Lighting measurement and assessments require the shut off of the breaker/power to select circuits to allow for measurements of the emergency lighting system and to confirm if lighting levels are adequate. Will need to de-energize escalators during non-revenue to measure light on adjacent stairs (normal power only to escalators). KCM EIC required. | N | N | Facilities
Mobilitie/Turnure Telecom Cole Edinger 206-473-1380 | P22-12-335 | Nick Datz 206-398-5236 | KCM CANCELLED, no support | 44914 | 44918 | 0001 | 0400 | Westlake Station- Platform, NB towards Convention Place and SB from Convention Place | Troubleshoot cellular infrastructure (DAS) located at Westlake Station (Platform level) along with accessing the antennas/passive equipment located at NB & SB Tunnel between Westlake-Convention Place after revenue service. This will require a bucket truck. No power down until non-rev. KCM EIC and support required. | YES - not available | N | Signals, Traction Power
Centennial Contractors/United Professional Caulking (Unipro) Rob Crossland 253 861 4714 | P22-12-342 | Gita Monghate 206 604 0183 | KCM CANCELLED, no support SUBMITTED LATE/ACCEPTED | 44914 | 44917 | 0700 | 1600 | ALS Stairwells | Pressure wash the stairwells and replacing the sealant along the stairwell gutters. One stairwell at a time, will be blocked off at the top and bottom. Escalators and the other stairwell will remain open for use. Each stairwell takes one week to complete. Facilities EIC required. | N | N | Facilities
Waters Construction Chris Waters 206 321 3059 | P22-12-343 | Gita Monghate 206 604 0183 | KCM CANCELLED, no support SUBMITTED LATE/ACCEPTED | 44915 | 44916 | 0100 | 0500 | Columbia City Station Platform | Remove and replace 2 failing ADA warning tiles. Will have a generator, roto hammer, grinder, and shop vac onsite. Facilities EIC required. | N | N | Facilities
400 series
CTS Bert Woodson 253 306 6307 | P22-12-406 |  | KCM Cancelled- Facilities support is not available. | 44921 | 44923 | 0800 | 1600 | OMF- Parking Lot & Comm Room - Various vaults | OMF Data Cabling & Antenna Install. Installation of 01 new data cable to 01 location in parking lot. Test all new data cabling Install 01 antenna and antenna mount provided by others onto existing light pole. Will be using bucket truck for access. KCM EIC and support required. | N | N | SCADA, Facilities
Centennial Contractors/United Professional Caulking (Unipro) Rob Crossland 253 861 4714 | P22-12-409 | Gita Monghate 206 604 0183 | KCM Cancelled- Facilities support is not available. | 44922 | 44925 | 0700 | 1600 | ALS Stairwells | Pressure wash stairwells and replace sealant along the stairwell gutters. One stairwell at a time will be blocked off at the top and bottom. Escalators and the other stairwell will remain open for use. Facilities EIC required. | N | N | Facilities
Western Ventures/Metro Glass Taus Casswell 253-686-1308 | P22-12-411 | Gita Monghate/Levi Young 206-903-7180 | Cancelled per contractor | 44921 | 44925 | 0500 | 1600 | OMF- 4th Floor LCC, Server Room & Yard (outside VM shop on the backside) | HVAC Replacement - Remove windows, one in the LCC and one in the server room to allow for AC/Negative air exhaust. Plywood will be installed as a temporary window. A large boom will be used and will come within 10 ft of OCS. Lift will be delivered via flatbed truck. Fall protection required. KCM EIC and support required. Coordinate with Vehicle Maintenance. | YES - NM1 | N | Facilities, Traction Power, Vehicle Maintenance
Western Ventures/Vet First Taus Casswell 253-686-1308 | P22-12-412 | Gita Monghate/Levi Young 206-903-7180 | Cancelled per contractor | 44922 | 44925 | 0500 | 1600 | OMF- 4th Floor, 416 Room | HVAC Replacement - Install a Reverse Osmosis Filtration System in Rm. 416. This installation requires the shutdown of domestic cold water to allow for the final connection. The water shutdown will affect the whole building. KCM EIC required. | N | N | Facilities
Mobilitie/NW Signals Anthony Vivolo 206 612 3723 | P22-12-417 | Nick Datz 206 398 5236 | KCM Cancelled- Signals support is not available. | 44921 | 44925 | 0001 | 0400 | UWS Station, UWS NB Tunnel (Electrical Room - visual only), (CP 13 and CP 19) and Westlake Station | Troubleshoot the fiber connectivity on the cellular system component (DAS Remote). Will access thru NO5 into NO6, also need access to NB cross passage 13 & 19. KCM EIC required. | N | N | Signals
Mobilitie/NW Signals Anthony Vivolo 206 612 3723 | P22-12-418 | Nick Datz 206-398-5236 | KCM Cancelled- Signals support is not available. | 44921 | 44925 | 0001 | 0400 | Beacon Hill Station, NB and SB bore of Beacon Hill, CP1, CP2 and CP3 | Troubleshoot noise on the cellular system component (DAS Remote). Will carry a power meter to verify power feeding the remote units and clean fiber to restore connectivity. KCM EIC required. | N | N | Signals
Mobilitie/NW Signals Cole Edinger 206 473 1380 | P22-12-420 | Nick Datz 206 398 5236 | KCM Cancelled- Signals support is not available. | 44921 | 44925 | 0001 | 0400 | Westlake Station- Platform, NB & SB Tunnel between Westlake-Convention Place | Troubleshoot cellular infrastructure (DAS) platform level along with accessing the antennas/passive equipment located at the NB & SB tunnel. Requires access to the DAS passive infrastructure (antennas, splitters) using a lift. KCM EIC and support required. | YES | N | Signals, Traction Power